## Sheet1
No | BRD No | Project/Fitur | PIC | Status | Priority | Tanggal Submit | Tanggal Completed | Catatan | uid
1 | BRD020 | Perubahan Password dan Body Email Institusi Client yang semula ddmmyyClientid menjadi mmyyyyClientID | Martin Haudy | Competed | High | 2025-04-24 | 2025-05-30 | test | f54c395c-9fdb-4d76-8f82-edb2f47ab5bf
2 | BRD021 | Add "Unit Registry" module (Mutual Fund) In S21 Internal Audit | Yoga Dishtira | Completed | High | 2025-07-18 | 2025-10-27 |  | 5040b0d1-6635-48d4-8e6d-33183bcf3509
3 | BRD022 | Operation Purpose and Compliance Request | Yoga Dishtira | Completed | High | 2025-05-07 | 2025-05-16 |  | 60e77c22-31bf-4f69-a24c-e5637781a9c2
4 | BRD023 | Penyesuaian Ajustment ARB 15% Ketentuan bursa tanggal 8 April 2025 | David Steven | Completed | High | 2025-04-08 | 2025-04-18 |  | a82a3b4a-f22f-4abd-b515-75ddb95de970
5 | BRD024 | Corporate Action Advice for Merger FREN and EXCL | Yoga Dishtira | Completed | High | 2025-04-22 | 2025-05-02 |  | d4ab9c4d-e11c-4daf-82d6-683020823f8e
6 | BRD025 | Perubahan Signature pada notification Letter S21 - Notification Closed Account -Notification for change of sales | Martin Haudy | Completed | High | 2025-04-24 | 2025-05-30 |  | c66bdbb9-080b-4a9d-99e0-d4ee5bcc6ed2
7 | BRD026 | Trade Recapitulation By Trade | Yoga Dishtira | Completed | High | 2025-01-02 | 2025-01-08 |  | 57358f21-6a5a-4b33-9a7a-1d0b4d401d96
8 | BRD027 | BDV Promotion ( - Setting ODT otomatis (Buy Hi Sell Hi) pada client maintenance -field- Day Trade untuk nasabah regular individu online Trading , -Setting Perubahan Data untuk Nasabah Existing regular individu online trading pada client maintenance -field day trade- Buy Hi Sell Hi (list nasabah terlampir) | Yoga Dishtira | Completed | High | 2025-02-04 | 2025-02-11 |  | 8cf6061f-eb3b-4d48-8f4c-9b7ed25d16e0
9 | BRD028 | Company Requirement (Modification Client CIF Institutional and individual, additional field all client list, additional field client list Part 1, Modification Search Client (F6) | Yoga Dishtira | Completed | High | 2025-01-17 | 2025-01-22 |  | 63ace90c-f793-4c43-9346-a5fc04c8e620
10 | BRD029 | Penambahan Field Client List "By Created Date" | Yoga Dishtira | Completed | High | 2025-01-30 | 2025-02-10 |  | 6a57a992-b2bb-464f-bc06-c811b7358cff
11 | BRD030 | 1.Stamping Report DJP 2.Final Income Tax Witholding Report for Stock Sale Transaction | Yoga Dishtira | Completed | High | 2025-02-04 | 2025-02-07 |  | 2c12e95e-ecbf-45bb-890c-32c8abebee18
12 | BRD031 | Webconsole (mobile) server | David Steven | Completed | High | 2025-01-17 | 2025-01-20 |  | df1591e9-ac80-44b5-bbcf-2cd136f06ce1
13 | BRD033 | Report Client Trade Activity | Yoga Dishtira | Completed | High | 2025-02-28 | 2025-04-10 |  | a1c7f87c-7efe-4ef3-aea6-2ec40782a8ea
14 | BRD034 | Modify Client List Report | Yoga Dishtira | Completed | High | 2024-11-11 | 2025-04-10 |  | 4936e7ea-549b-4767-b5a2-e81e605117c4
15 | BRD035 | 1. Penonaktifkan Program Promo One Day Trade (ODT), Update schema commision tanpa ODT fee, 3. Pembahasan akses Client Commision | Yoga Dishtira | Completed | High | 2025-09-17 | 2025-09-30 |  | 2411501a-555c-42c7-b751-eff37276f30c
16 | BRD036 | Menghilangkan password untuk pdf protection di SOA pada akses web report | Martin Haudy | Completed | High | 2025-10-02 | 2025-12-05 | Sudah Naik ke PROD, Konfirmasi ke Tim Ebiz | c257ead8-a5b8-4ba0-9b31-8d21f60a6052
17 | BRD037 | Update Web banner pada slide 5 dari important Notice Menjadi Utrade New Look | David Steven | Completed | High | 2025-10-02 | 2025-10-03 |  | 9be398f3-52e2-4f31-bb7d-7fa5ed9fb897
18 | BRD038 | Penghapusan Profil Ibu Yacinta di website Perusahaan | Yoga Dishtira | Completed | High | 2025-10-03 | 2025-10-03 |  | 3f98739e-10e7-4ce1-ba93-fe7b9f6dfd28
19 | BRD040 | Report Statement of Account Report Trade ConfirmationLaporan Transaksi Anggota Bursa (.LTH) , Modify TC Equity Format dan New Format Laporan Transaksi Equity | Yoga Dishtira | Completed | High | 2025-02-24 | 2025-04-09 |  | 35b7640b-24d7-439d-b546-0a9de951a809
20 | BRD041 | Update Website - Banner Change Password | David Steven | Completed | High | 2025-10-08 | 2025-10-10 |  | fdfd9c9e-2965-45fc-8994-88a2e162523b
21 | BRD042 | Upload Banner UTRADE Apps all device | Deni, Eko | Completed | High | 2025-10-08 | 2025-10-17 |  | bc56d9b3-433f-413b-9185-7ab41e01be45
22 | BRD043 | Menambahkan setting colour untuk tombol order Buy/Sell pada UTRADE Apps | Gilang Setiawan, Deni, Dimas | On Progress | High | 2025-10-15 |  | Desktop blum, mobile blum , web sudah tapi blum di masukan setting | 7e89ba1d-3f6b-4cbc-8c74-71d05f644d71
23 | BRD044 | Permintaan penyesuian letter pada 1. Utrade account aktivasi di BO terkait password complaxity 2. CMS reset password & PIN | David | On Progress | High | 2025-10-07 |  | Sudah Naik ke PROD, menunggu penyesuian dari pak david yang di email ibu Hera baru | 87514b3f-0e2b-45c0-bc3f-8eb19a6f929a
24 | BRD045 | Penambahan Kolom Kekayaan Bersih dan Penghapusan Kolom Asset di CIF Maintenance dan Tarikan Client List | Yoga Dishtira | Completed | High | 2025-10-16 | 2025-12-24 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim CS | 7a86677d-9ef9-4094-91f3-69595c472caa
25 | BRD046 | Perubahan email tujuan pelaporan pelanggaran di website Utrade | David Steven | Completed |  | 2025-10-14 | 2025-10-23 |  | 6e25705b-7eb0-4163-bd9b-62f6d27453aa
26 | BRD047 | Perubahan Nomor Rekening Bank untuk Transaksi RDN | Yoga Dishtira | Completed |  | 2025-10-22 | 2025-11-08 |  | 50bfdf43-5088-4f6e-8d37-78ed76bc2ab0
27 | BRD048 | Change Mapping MKBD VD 6.6 and update saving balance reconciliation - bank KSEI | Yoga Dishtira | Completed | High | 2025-10-22 | 2025-11-25 |  | 04d114e6-6168-4fa6-a86a-a1acea5bb92c
28 | BRD049 | Redirect Website dari kh.co.id ke utrade.co.id | David | On Progress | High | 2025-11-27 |  | masih on proggress sudah kirim sertifikat ke singapura dari singapura akan meregister sertifikatnya. | 6985d1cb-2af2-4a0d-a05e-21cab2e3fcff
29 | BRD050 | Perubahan Logo UTRADE pada Website dan aplikasi UTRADE (Desktop, Website dan Mobile) | David,Gilang,Dimas, Deni | Completed | High | 2025-11-17 | 2025-12-19 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | e1a31c21-631d-4d11-8d2d-42b7a0bfd5e4
30 | BRD051 | Perubahan Nama PT Kay Hian Sekuritas pada Website | David Steven | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 2501f577-b69e-4d5a-b3c8-68d429aa4eba
31 | BRD052 | Perubahan Nama PT pada UTRADE all Apps | Gilang, Dimas, Deni | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 45b5711d-6dac-4db7-8d8a-ddfd6b39f730
32 | BRD053 | Migrasi Web Report dan Web Research ke IP Local | David | Completed | High | 2025-12-03 |  | Sudah di pindahkan migrasi ke Local webreport dan web research, menunggu Make sure dari tim Ebiz, info update ke david mengenai statusnya (sudah ok atau belum) | 0e2aa8b5-f282-4663-ad92-f45a8aa90b78
33 | BRD054 | Perubahan nama PT dan Perubahan Logo PT di S21 Remote Trading | Nabila | On Progress | High | 2025-12-05 |  | Menunggu update dari Nabila | 4c9191ec-95e1-4447-a8b4-68ae973e5d0a
34 | BRD055 | Perubahan nama PT dan Perubahan Logo PT di S21 Back Office | Yoga Dishtira | Completed | High | 2025-12-17 | 2025-12-22 | Ubah logo manual ke user user yang blum ada logo di S21 BO Semua Divisi | 4b9d630b-bc19-4080-b2ee-2d5e5b2ebd48
35 | BRD057 | Password Complexity S21 RT | Billy | Completed | High | 2025-10-01 | 2025-10-03 |  | 57773c99-ca8d-4160-b8b7-e23613d19654
36 | BRD058 | 1. Unlock Mandatory data pada CIF Maintenance Institutional | Yoga Dishtira | On Progress | High | 2025-12-17 |  | Sudah di implementasikan di development , Test oleh Tim CS | 101a1573-4392-4aed-b5e1-8f2f4e33934a
37 | BRD059 | Change Notification Letter | Martin Haudy | On Progress | High | 2025-12-17 |  | Permintaan SP S21Notification dari Tim S21 | 109131f7-8fe5-4462-a065-4920fa74b93e
38 | BRD060 | Menu Watch List Automatic Risk Profile Nasabah Menjadi High Risk CIF Insitutional | Yoga Dishtira | Completed | High | 2025-12-22 | 2025-12-24 | Sudah di PROD, Menunggu Konfirmasi dari Tim CS | d4b0004f-4a74-45e5-bc42-2c0f6330db74
39 | BRD001 | Penambahan Dokumen Perjanjian Rekening Efek dan Ketentuan Pelindungan Data Pribadi | Yoga Dishtira | Completed | High | 2025-07-11 | 2025-07-14 | Done Bikin UAT dan CR | b2310609-a854-4ff3-a979-f540d3cd0926
40 | BRD002 | Additional View Mode TC Equity (Sending Trade Settlement) | Yoga Dishtira | Completed | High | 2025-02-28 | 2025-03-21 |  | 118f909b-9cc7-4afa-b6ba-e3d22d30a226
41 | BRD004 | List of Fixed Assets | Yoga Dishtira | Completed | High | 2025-02-28 | 2025-03-21 |  | 7d12c2e9-1a14-4079-8dd0-a5b84e0dd9ec
42 | BRD005 | Update Web Banner hari raya Nyepi dan Hari Raya idul Fitri | David Seven | Completed | High | 2025-03-26 | 2025-03-28 |  | 26bddb6c-dd97-4ad6-bbb6-122108c5e188
43 | BRD006 | Modification request : create new page - utrade.co.id | David Steven | Completed | High | 2025-03-10 | 2025-03-14 |  | 12e3c227-424e-469b-8fb9-aa11a7430491
44 | BRD007 | Menambahkan link berisi dokumen perjanjian pembukaan rekening efek dan kebijakan perlindungan data pribadi pada TC | Yoga Dishtira | Completed | High | 2025-09-08 | 2025-09-19 |  | ae4dc2dc-a1db-493b-aae7-f0df306a63fd
45 | BRD008 | Penambahan Kolom PEP dan Compliance watchlist untuk tarikan list client report | Yoga Dishtira | Completed | High | 2025-08-07 | 2025-08-14 |  | 302f7f25-1c5b-4b5e-a91b-add812506ddc
46 | BRD009 | Penambahan Report Mutual Fund Unit Registry | Chintya | Completed | High | 2025-09-12 | 2025-10-20 |  | 2dbe65dd-d068-4400-9e78-9bb048c3ccb6
47 | BRD010 | Perubahan Proses Penyampaian informasi mengenai saham pada papan akselarasi | Yoga Dishtira | Completed | High | 2025-04-27 | 2025-05-09 |  | 5cc58511-06d1-4da1-a2e9-29bad204945d
48 | BRD011 | Perubahaan Parameter Unusual Transaction Volume | Yoga Dishtira | Completed | High | 2025-08-12 | 2025-12-22 | Done Bikin UAT dan CR | cd62773f-4b3a-43d6-8fb8-6092e38d5b22
49 | BRD012 | Penghapusan Settingan Komisi dengan Skema Daytrade menjadi Nol(0) per Oktober 2025 | Yoga Dishtira | Completed | High | 2025-09-15 | 2025-09-30 |  | 9667b41f-9adb-4551-9f8c-b5a336db999a
50 | BRD013 | Unlock Mandatory Data pada CIF Maintance | Yoga Dishtira | Completed | High | 2025-08-14 | 2025-09-30 |  | 56ecfd5c-1842-4d3a-a64d-ddc5092cfff0
51 | BRD014 | 1.Format baru Trade Confirmation 2. Penambahan Stamping Proteksi Password pada Trade Confirmation untuk Product Bond (IPO dan Secondary) 3. Pengaktiffan Realtime Order dan Trade Kembali | Yoga Dishtira | Completed | High | 2025-09-17 | 2025-09-27 |  | 6ce2e46c-b054-465f-ba73-73b24d20f40e
52 | BRD015 | Penyesuaian format passsword protection pdf (pada reset password & pin utrade) | Martin Haudy | On Progress | High | 2025-09-15 |  | Pengecekan dari pak Martin S21 | e622c91f-fb5f-418d-a0a7-157dbfea93d9
53 | BRD016 | added another Field in Report Client list Part 3 | Yoga Dishtira | Completed | High | 2025-05-14 | 2025-05-23 |  | 41c24eea-c37c-437a-9ce1-9144e06e2065
54 | BRD017 | Stock position for group with zero balance | Yoga Dishtira | Completed | High | 2025-06-24 | 2025-07-09 |  | 2147a7c7-1391-43ad-8efc-68aa81637990
55 | BRD018 | 1. Unlock Mandatory Data pada CIF Maintance 2.Tampilkan Field TIN yang ada di CIF maintance pada client Maintance(Regulator Requirement) | Yoga Dishtira | Completed | High | 2025-08-14 | 2025-06-16 |  | ec66942d-2ff1-4c4d-a88f-3c1eb5682004
56 | BRD019 | Penyesuaian tampilan excel file - contracting: Trade Recapitulation | Yoga Dishtira | Completed | High | 2025-07-24 | 2025-08-04 |  | 1466a435-8d4c-47ed-8d03-5efbc4f4d0a6
57 | BRD020 | Perubahan Password dan Body Email Institusi Client yang semula ddmmyyClientid menjadi mmyyyyClientID | Martin Haudy | Completed | High | 2025-04-24 | 2025-05-30 |  | 84b077d8-3ee6-487b-a248-5a05cb5995fd
58 | BRD021 | Add "Unit Registry" module (Mutual Fund) In S21 Internal Audit | Yoga Dishtira | Completed | High | 2025-07-18 | 2025-10-27 |  | d3d5fe8e-5b25-4e94-86f9-e7bc70293036
59 | BRD022 | Operation Purpose and Compliance Request | Yoga Dishtira | Completed | High | 2025-05-07 | 2025-05-16 |  | ade7bb5e-9d9f-4f46-8bf0-e8df595954ab
60 | BRD023 | Penyesuaian Ajustment ARB 15% Ketentuan bursa tanggal 8 April 2025 | David Steven | Completed | High | 2025-04-08 | 2025-04-18 |  | 4e018bd2-8611-40fd-b7f8-48aeaae5eabc
61 | BRD024 | Corporate Action Advice for Merger FREN and EXCL | Yoga Dishtira | Completed | High | 2025-04-22 | 2025-05-02 |  | a20227f2-d025-4023-a8a4-b4ae44029ad9
62 | BRD025 | Perubahan Signature pada notification Letter S21 - Notification Closed Account -Notification for change of sales | Martin Haudy | Completed | High | 2025-04-24 | 2025-05-30 |  | f532aa4a-3b9d-449b-9832-dd81d15de732
63 | BRD026 | Trade Recapitulation By Trade | Yoga Dishtira | Completed | High | 2025-01-02 | 2025-01-08 |  | 3bf77f75-bb05-43c1-9fbd-e23fa43746a3
64 | BRD027 | BDV Promotion ( - Setting ODT otomatis (Buy Hi Sell Hi) pada client maintenance -field- Day Trade untuk nasabah regular individu online Trading , -Setting Perubahan Data untuk Nasabah Existing regular individu online trading pada client maintenance -field day trade- Buy Hi Sell Hi (list nasabah terlampir) | Yoga Dishtira | Completed | High | 2025-02-04 | 2025-02-11 |  | 5ba17118-0a35-4ff9-a84d-cdb6fc68d949
65 | BRD028 | Company Requirement (Modification Client CIF Institutional and individual, additional field all client list, additional field client list Part 1, Modification Search Client (F6) | Yoga Dishtira | Completed | High | 2025-01-17 | 2025-01-22 |  | 0c4f0c37-9b78-440d-9525-c43c1d04ee5c
66 | BRD029 | Penambahan Field Client List "By Created Date" | Yoga Dishtira | Completed | High | 2025-01-30 | 2025-02-10 |  | 91d8ccbd-baac-4e4a-8951-91a6ce12bf87
67 | BRD030 | 1.Stamping Report DJP 2.Final Income Tax Witholding Report for Stock Sale Transaction | Yoga Dishtira | Completed | High | 2025-02-04 | 2025-02-07 |  | 6c2ae017-0933-46b4-a7f5-997962769596
68 | BRD031 | Webconsole (mobile) server | David Steven | Completed | High | 2025-01-17 | 2025-01-20 |  | 97876b70-96b2-4509-ab8f-7cb600e504a1
69 | BRD033 | Report Client Trade Activity | Yoga Dishtira | Completed | High | 2025-02-28 | 2025-04-10 |  | 0eac1158-0512-4ed7-8299-ca67360849b6
70 | BRD034 | Modify Client List Report | Yoga Dishtira | Completed | High | 2024-11-11 | 2025-04-10 |  | 7ff48960-8753-43bc-899c-3c838d63bb3a
71 | BRD035 | 1. Penonaktifkan Program Promo One Day Trade (ODT), Update schema commision tanpa ODT fee, 3. Pembahasan akses Client Commision | Yoga Dishtira | Completed | High | 2025-09-17 | 2025-09-30 |  | 105ea383-0f96-4335-ab34-8a132d49a182
72 | BRD036 | Menghilangkan password untuk pdf protection di SOA pada akses web report | Martin Haudy | Completed | High | 2025-10-02 | 2025-12-05 | Sudah Naik ke PROD, Konfirmasi ke Tim Ebiz | 487c4c47-92c7-42b5-a6f1-1830a26eaba4
73 | BRD037 | Update Web banner pada slide 5 dari important Notice Menjadi Utrade New Look | David Steven | Completed | High | 2025-10-02 | 2025-10-03 |  | e74edebd-6e06-4acb-9a62-ba9fac47b090
74 | BRD038 | Penghapusan Profil Ibu Yacinta di website Perusahaan | Yoga Dishtira | Completed | High | 2025-10-03 | 2025-10-03 |  | 8de63a82-b55c-4e75-b997-dc0670e2cf3e
75 | BRD040 | Report Statement of Account Report Trade ConfirmationLaporan Transaksi Anggota Bursa (.LTH) , Modify TC Equity Format dan New Format Laporan Transaksi Equity | Yoga Dishtira | Completed | High | 2025-02-24 | 2025-04-09 |  | ff89ab4c-fb55-46cf-b6a7-a3aa375f4ba8
76 | BRD041 | Update Website - Banner Change Password | David Steven | Completed | High | 2025-10-08 | 2025-10-10 |  | f2c0983b-7da0-41bd-94f1-3bc0fc8ba03c
77 | BRD042 | Upload Banner UTRADE Apps all device | Deni, Eko | Completed | High | 2025-10-08 | 2025-10-17 |  | 588bada3-57a2-4e07-a793-9e1bb7de5ee5
78 | BRD043 | Menambahkan setting colour untuk tombol order Buy/Sell pada UTRADE Apps | Gilang Setiawan, Deni, Dimas | On Progress | High | 2025-10-15 |  | Desktop blum, mobile blum , web sudah tapi blum di masukan setting | d1a6d91d-a846-4a47-b893-e7b26ddeb686
79 | BRD044 | Permintaan penyesuian letter pada 1. Utrade account aktivasi di BO terkait password complaxity 2. CMS reset password & PIN | David | On Progress | High | 2025-10-07 |  | Sudah Naik ke PROD, menunggu penyesuian dari pak david yang di email ibu Hera baru | df2b5f68-3f65-48ac-ae14-6a6a7b2ae902
80 | BRD045 | Penambahan Kolom Kekayaan Bersih dan Penghapusan Kolom Asset di CIF Maintenance dan Tarikan Client List | Yoga Dishtira | Completed | High | 2025-10-16 | 2025-12-24 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim CS | 7e499106-c2ce-4ed1-a282-a317c5f7f936
81 | BRD046 | Perubahan email tujuan pelaporan pelanggaran di website Utrade | David Steven | Completed |  | 2025-10-14 | 2025-10-23 |  | 7541ff9a-cd98-4efa-a018-b17200c11c5f
82 | BRD047 | Perubahan Nomor Rekening Bank untuk Transaksi RDN | Yoga Dishtira | Completed |  | 2025-10-22 | 2025-11-08 |  | b2e49739-95a4-4930-9761-341f2b3fcb48
83 | BRD048 | Change Mapping MKBD VD 6.6 and update saving balance reconciliation - bank KSEI | Yoga Dishtira | Completed | High | 2025-10-22 | 2025-11-25 |  | 8982005c-21d8-4d64-9f49-8134c6b8aacd
84 | BRD049 | Redirect Website dari kh.co.id ke utrade.co.id | David | On Progress | High | 2025-11-27 |  | masih on proggress sudah kirim sertifikat ke singapura dari singapura akan meregister sertifikatnya. | 21957554-4ee5-41d7-8f98-f6dbf10c12a5
85 | BRD050 | Perubahan Logo UTRADE pada Website dan aplikasi UTRADE (Desktop, Website dan Mobile) | David,Gilang,Dimas, Deni | Completed | High | 2025-11-17 | 2025-12-19 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 81407cee-9ec7-4cc6-9e18-36924309a1ec
86 | BRD051 | Perubahan Nama PT Kay Hian Sekuritas pada Website | David Steven | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 4d9842d6-f7b4-4322-b131-a4aaa17e05f2
87 | BRD052 | Perubahan Nama PT pada UTRADE all Apps | Gilang, Dimas, Deni | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 9e69123e-abf8-4848-ae61-cab5a4820a95
88 | BRD053 | Migrasi Web Report dan Web Research ke IP Local | David | Completed | High | 2025-12-03 |  | Sudah di pindahkan migrasi ke Local webreport dan web research, menunggu Make sure dari tim Ebiz, info update ke david mengenai statusnya (sudah ok atau belum) | 9469ded6-030c-4d19-b8c6-ce43549c979e
89 | BRD054 | Perubahan nama PT dan Perubahan Logo PT di S21 Remote Trading | Nabila | On Progress | High | 2025-12-05 |  | Menunggu update dari Nabila | 75c3fa7c-dddd-48cf-88aa-1b62ec84df10
90 | BRD055 | Perubahan nama PT dan Perubahan Logo PT di S21 Back Office | Yoga Dishtira | Completed | High | 2025-12-17 | 2025-12-22 | Ubah logo manual ke user user yang blum ada logo di S21 BO Semua Divisi | 9a995b34-7bea-4190-9569-b730f543bdb3
91 | BRD057 | Password Complexity S21 RT | Billy | Completed | High | 2025-10-01 | 2025-10-03 |  | 00533daf-d219-4c19-a1d3-a421a7e2fcd7
92 | BRD058 | 1. Unlock Mandatory data pada CIF Maintenance Institutional | Yoga Dishtira | On Progress | High | 2025-12-17 |  | Sudah di implementasikan di development , Test oleh Tim CS | 0ba91190-91bb-43da-a8dd-4f7d02749185
93 | BRD059 | Change Notification Letter | Martin Haudy | On Progress | High | 2025-12-17 |  | Permintaan SP S21Notification dari Tim S21 | 98cf8da6-43c7-4155-85dd-c435da78024f
94 | BRD060 | Menu Watch List Automatic Risk Profile Nasabah Menjadi High Risk CIF Insitutional | Yoga Dishtira | Completed | High | 2025-12-22 | 2025-12-24 | Sudah di PROD, Menunggu Konfirmasi dari Tim CS | eccc4785-98a8-43c3-9ac6-9838c061917a
95 | BRD101 | Project 29 | Yoga Dishtira | New | Urgent | 2025-12-24 | 2025-12-27 |  | bc3e47a9-7e63-45ab-a1d9-7146fac8a816
96 | BRD0074 | Project 294 | Yoga Dishtira | New | High | 2025-12-26 |  | t | a29e9cc1-ba96-4213-a1dd-4a7a4b25025f