## Sheet1
No | BRD No | Project/Fitur | Link BRD | PIC | Contact Person | Status | Priority | Tanggal Submit | Tanggal Completed | Catatan | uid
1 | BRD009 | Penambahan Report Mutual Fund Unit Registry |  | Chintya | Meiliani Intania | New | High | 2025-09-12 | 2025-10-20 |  | d34a601b-fccd-4fcd-804c-7c36f07a4f54
2 | BRD010 | Perubahan Proses Penyampaian informasi mengenai saham pada papan akselarasi |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | Medium | 2025-04-27 | 2025-05-09 |  | 089fa779-ff79-4c86-b21b-c25429188566
3 | BRD011 | Perubahaan Parameter Unusual Transaction Volume |  | Yoga Dishtira | Yandhika Mardi Haposan | Pending | High | 2025-08-12 | 2025-12-22 | Done Bikin UAT dan CR | be380aa6-ca51-4d26-b2ed-13bcab8ac1c6
4 | BRD012 | Penghapusan Settingan Komisi dengan Skema Daytrade menjadi Nol(0) per Oktober 2025 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Low | 2025-09-15 | 2025-09-30 |  | 79a62734-cab3-4dba-bf9e-c0b94fb37521
5 | BRD013 | Unlock Mandatory Data pada CIF Maintance |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Urgent | 2025-08-14 | 2025-09-30 |  | e921c181-916a-44b5-884b-f355e81b88a6
6 | BRD014 | 1.Format baru Trade Confirmation 2. Penambahan Stamping Proteksi Password pada Trade Confirmation untuk Product Bond (IPO dan Secondary) 3. Pengaktiffan Realtime Order dan Trade Kembali |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-09-17 | 2025-09-27 |  | da3092eb-5bc5-4be7-9c66-685ceba994eb
7 | BRD015 | Penyesuaian format passsword protection pdf (pada reset password & pin utrade) |  | Martin Haudy | Indri Ariyani | In Progress | Low | 2025-09-15 |  | Pengecekan dari pak Martin S21 | 348999ad-8c79-491f-b8ef-835788ede478
8 | BRD016 | added another Field in Report Client list Part 3 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-14 | 2025-05-23 |  | 01872dfd-05eb-44d6-8e93-2689110b15b1
9 | BRD017 | Stock position for group with zero balance |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-06-24 | 2025-07-09 |  | 949bf0c5-a20c-44d1-9f2f-bf18b16de5ac
10 | BRD018 | 1. Unlock Mandatory Data pada CIF Maintance 2.Tampilkan Field TIN yang ada di CIF maintance pada client Maintance(Regulator Requirement) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-08-14 | 2025-06-16 |  | d619082e-c85b-41f0-9ed0-feb4e821b023
11 | BRD019 | Penyesuaian tampilan excel file - contracting: Trade Recapitulation |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-07-24 | 2025-08-04 |  | f6438346-984b-4f45-b312-0a736fa7b309
12 | BRD020 | Perubahan Password dan Body Email Institusi Client yang semula ddmmyyClientid menjadi mmyyyyClientID |  | Martin Haudy | Meiliani Intania | Completed | High | 2025-04-24 | 2025-05-30 |  | 14a344c1-b4c5-4046-b5b7-b7d3b55fdcf9
13 | BRD021 | Add "Unit Registry" module (Mutual Fund) In S21 Internal Audit |  | Yoga Dishtira | Jeanny Novianti Cahyadi | Completed | High | 2025-07-18 | 2025-10-27 |  | 21afaf08-e6ee-4ec5-a8d2-d9f402e868e5
14 | BRD022 | Operation Purpose and Compliance Request |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-07 | 2025-05-16 |  | 0040d586-db04-4f81-a505-988a3a6b011c
15 | BRD023 | Penyesuaian Ajustment ARB 15% Ketentuan bursa tanggal 8 April 2025 |  | David Steven | Indri Ariyani | Completed | High | 2025-04-08 | 2025-04-18 |  | 6e77cc49-22d2-492e-bb9f-7913e1f33405
16 | BRD024 | Corporate Action Advice for Merger FREN and EXCL |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-04-22 | 2025-05-02 |  | 33b0d567-ef56-4fed-b356-f89ba34b3494
17 | BRD025 | Perubahan Signature pada notification Letter S21 - Notification Closed Account -Notification for change of sales |  | Martin Haudy | Suci Yulianti Ayunita Putri | Completed | High | 2025-04-24 | 2025-05-30 |  | b764af96-18a4-4cc8-8d26-ed84ef299472
18 | BRD026 | Trade Recapitulation By Trade |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-01-02 | 2025-01-08 |  | 2cef0d73-2125-4197-8b9a-7d604b2e28f1
19 | BRD027 | BDV Promotion ( - Setting ODT otomatis (Buy Hi Sell Hi) pada client maintenance -field- Day Trade untuk nasabah regular individu online Trading , -Setting Perubahan Data untuk Nasabah Existing regular individu online trading pada client maintenance -field day trade- Buy Hi Sell Hi (list nasabah terlampir) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-02-04 | 2025-02-11 |  | 5a58abbc-bdf7-4d3f-9647-8378c4ad4919
20 | BRD028 | Company Requirement (Modification Client CIF Institutional and individual, additional field all client list, additional field client list Part 1, Modification Search Client (F6) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-17 | 2025-01-22 |  | 0fa414a7-12a8-4a3b-9a82-ea24daf3de6a
21 | BRD029 | Penambahan Field Client List "By Created Date" |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-30 | 2025-02-10 |  | 744f0cd7-42da-4060-abe5-5fd14401016f
22 | BRD030 | 1.Stamping Report DJP 2.Final Income Tax Witholding Report for Stock Sale Transaction |  | Yoga Dishtira | Tjoa Lisa | Completed | High | 2025-02-04 | 2025-02-07 |  | d3efc9c8-329f-4f35-b17f-582db20c96fc
23 | BRD031 | Webconsole (mobile) server |  | David Steven | Indri Ariyani | Completed | High | 2025-01-17 | 2025-01-20 |  | 1d300322-7b38-40c1-a4d3-f2b50a435f43
24 | BRD033 | Report Client Trade Activity |  | Yoga Dishtira | Adelia Haryanto | Completed | High | 2025-02-28 | 2025-04-10 |  | 8270f2b6-ce48-4204-8169-03cbf0079d67
25 | BRD034 | Modify Client List Report |  | Yoga Dishtira | Olivia Penthesilea | Completed | High | 2024-11-11 | 2025-04-10 |  | 30e6800e-5acf-4a23-ad82-0848d654f642
26 | BRD035 | 1. Penonaktifkan Program Promo One Day Trade (ODT), Update schema commision tanpa ODT fee, 3. Pembahasan akses Client Commision |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-09-17 | 2025-09-30 |  | b97b4fe5-73fe-4a88-b450-6eaec8576f90
27 | BRD036 | Menghilangkan password untuk pdf protection di SOA pada akses web report |  | Martin Haudy | Indri Ariyani | Completed | High | 2025-10-02 | 2025-12-05 | Sudah Naik ke PROD, Konfirmasi ke Tim Ebiz | 1617fdb8-9b9f-4996-968f-c8ba93579638
28 | BRD037 | Update Web banner pada slide 5 dari important Notice Menjadi Utrade New Look |  | David Steven | Indri Ariyani | Completed | High | 2025-10-02 | 2025-10-03 |  | 283abbc8-1b5b-480b-a45e-bf7744938fae
29 | BRD038 | Penghapusan Profil Ibu Yacinta di website Perusahaan |  | Yoga Dishtira | Indri Ariyani | Completed | High | 2025-10-03 | 2025-10-03 |  | 84a0a79e-eb4c-49e4-bb9c-52a6d97a85e3
30 | BRD040 | Report Statement of Account Report Trade ConfirmationLaporan Transaksi Anggota Bursa (.LTH) , Modify TC Equity Format dan New Format Laporan Transaksi Equity |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-02-24 | 2025-04-09 |  | 8a1ade9f-9f50-4580-b601-6426309ec9e3
31 | BRD041 | Update Website - Banner Change Password |  | David Steven | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-10 |  | a2e77c17-46ba-420c-af62-38b5b57e252b
32 | BRD042 | Upload Banner UTRADE Apps all device |  | Deni, Eko | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-17 |  | b89b9ea0-cb22-4e0a-8cdb-7fb6ca5c0395
33 | BRD043 | Menambahkan setting colour untuk tombol order Buy/Sell pada UTRADE Apps |  | Gilang Setiawan, Deni, Dimas | Indri Ariyani | In Progress | High | 2025-10-15 |  | Desktop blum, mobile blum , web sudah tapi blum di masukan setting | 59477825-c258-4d61-9c4e-de2ca7997640
34 | BRD044 | Permintaan penyesuian letter pada 1. Utrade account aktivasi di BO terkait password complaxity 2. CMS reset password & PIN |  | David | Indri Ariyani | In Progress | High | 2025-10-07 |  | Sudah Naik ke PROD, menunggu penyesuian dari pak david yang di email ibu Hera baru | abe29478-6bce-4608-856f-0636d6e973de
35 | BRD045 | Penambahan Kolom Kekayaan Bersih dan Penghapusan Kolom Asset di CIF Maintenance dan Tarikan Client List |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-10-16 | 2025-12-24 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim CS | 190213b4-a96c-482a-819f-eba88ae70a6e
36 | BRD046 | Perubahan email tujuan pelaporan pelanggaran di website Utrade |  | David Steven | Indri Ariyani | Completed |  | 2025-10-14 | 2025-10-23 |  | 4d5434ad-028b-4c80-a9a4-63bd884b1254
37 | BRD047 | Perubahan Nomor Rekening Bank untuk Transaksi RDN |  | Yoga Dishtira | Meiliani Intania | Completed |  | 2025-10-22 | 2025-11-08 |  | d9f19f54-c7f9-420c-87c2-6f90dbf696f8
38 | BRD048 | Change Mapping MKBD VD 6.6 and update saving balance reconciliation - bank KSEI |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-10-22 | 2025-11-25 |  | c343cf40-b9af-469d-94b7-1c8e6c10bd61
39 | BRD049 | Redirect Website dari kh.co.id ke utrade.co.id |  | David | Indri Ariyani | In Progress | High | 2025-11-27 |  | masih on proggress sudah kirim sertifikat ke singapura dari singapura akan meregister sertifikatnya. | 58b57324-aed8-4e1e-ac6a-fe66069fcf00
40 | BRD050 | Perubahan Logo UTRADE pada Website dan aplikasi UTRADE (Desktop, Website dan Mobile) |  | David,Gilang,Dimas, Deni | Indri Ariyani | Completed | High | 2025-11-17 | 2025-12-19 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 79753af1-670a-4173-b04e-e69d947bc02d
41 | BRD051 | Perubahan Nama PT Kay Hian Sekuritas pada Website |  | David Steven | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | ef914a6b-c3f5-4823-aeb8-f018cb582de2
42 | BRD052 | Perubahan Nama PT pada UTRADE all Apps |  | Gilang, Dimas, Deni | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 3d6cc2c1-7e95-4550-b5a6-6225c6f19c46
43 | BRD053 | Migrasi Web Report dan Web Research ke IP Local |  | David | Indri Ariyani | Completed | High | 2025-12-03 |  | Sudah di pindahkan migrasi ke Local webreport dan web research, menunggu Make sure dari tim Ebiz, info update ke david mengenai statusnya (sudah ok atau belum) | 93e733f7-01b6-46b2-b80c-dab7265ed8e1
44 | BRD054 | Perubahan nama PT dan Perubahan Logo PT di S21 Remote Trading |  | Nabila | Rizky Saputra | In Progress | High | 2025-12-05 |  | Menunggu update dari Nabila | 3ce60eea-c4ce-4a83-8bea-57d43f5e2f4a
45 | BRD055 | Perubahan nama PT dan Perubahan Logo PT di S21 Back Office |  | Yoga Dishtira | Rizky Saputra | Completed | High | 2025-12-17 | 2025-12-22 | Ubah logo manual ke user user yang blum ada logo di S21 BO Semua Divisi | d2b607cd-83f9-4015-a503-102c65c6c99b
46 | BRD057 | Password Complexity S21 RT |  | Billy | Rizky Saputra | Completed | High | 2025-10-01 | 2025-10-03 |  | bc9dcf3d-30e8-47e5-9e34-4801cf068775
47 | BRD058 | 1. Unlock Mandatory data pada CIF Maintenance Institutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Sudah di implementasikan di development , Test oleh Tim CS | 5340a599-e078-4bfc-a559-cf24f8b8bde0
48 | BRD059 | Change Notification Letter |  | Martin Haudy | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Permintaan SP S21Notification dari Tim S21 | 5a88011f-1769-4243-a6be-c91c7ed7381f
49 | BRD060 | Menu Watch List Automatic Risk Profile Nasabah Menjadi High Risk CIF Insitutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-12-22 | 2025-12-24 | Sudah di PROD, Menunggu Konfirmasi dari Tim CS | 507fc7e4-8bbd-42b5-bcfe-86e9f2b7ca2d
50 | BRD02033 | tt4446 |  | gfhfghf | fhfggfgf | In Progress | High | 2025-12-01 |  |  | ac5f75aa-0dad-47e1-bddd-5512e99e19bd
51 | BRD020e | rr | https://id.linkedin.com/learning/ | Martin Haudy | Indriyani | In Progress | High | 2025-12-27 |  |  | 9efbccc4-4333-4d61-9c4e-d865ec232a11
52 | BRD0203 | reterrt | retet | retet | ertre | New | High |  | 2025-12-27 | rdgtrdgd | f0e16611-b690-425f-9acb-d4f29222544b
53 | BRD007 | Project 1 | test | Yoga Dishtira |  | In Progress | Medium | 2025-12-28 |  | test | f900ca81-61f6-4e7a-9246-32603b1e3ed1
54 | BRD008 | Penambahan Kolom PEP dan Compliance watchlist untuk tarikan list client report |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-08-07 | 2025-08-14 |  | b78eaa0a-cd33-4755-8524-82fd32dedb62
55 | BRD009 | Penambahan Report Mutual Fund Unit Registry |  | Chintya | Meiliani Intania | New | High | 2025-09-12 | 2025-10-20 |  | 5567e6b2-f6e8-42fa-9677-df2221ef4db0
56 | BRD010 | Perubahan Proses Penyampaian informasi mengenai saham pada papan akselarasi |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | Medium | 2025-04-27 | 2025-05-09 |  | de36252a-53a4-48a8-ba69-9e5c99f11394
57 | BRD011 | Perubahaan Parameter Unusual Transaction Volume |  | Yoga Dishtira | Yandhika Mardi Haposan | Pending | High | 2025-08-12 | 2025-12-22 | Done Bikin UAT dan CR | 3f5884b8-7e46-4c6a-bb7b-de5b06841749
58 | BRD012 | Penghapusan Settingan Komisi dengan Skema Daytrade menjadi Nol(0) per Oktober 2025 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Low | 2025-09-15 | 2025-09-30 |  | bc8355a3-fef8-49d6-835b-8d609d8be50b
59 | BRD013 | Unlock Mandatory Data pada CIF Maintance |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Urgent | 2025-08-14 | 2025-09-30 |  | 0567dcef-e916-407e-ab5e-6d2cf9a679a7
60 | BRD014 | 1.Format baru Trade Confirmation 2. Penambahan Stamping Proteksi Password pada Trade Confirmation untuk Product Bond (IPO dan Secondary) 3. Pengaktiffan Realtime Order dan Trade Kembali |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-09-17 | 2025-09-27 |  | b959f40c-75a4-4e28-9047-b2483a879a72
61 | BRD015 | Penyesuaian format passsword protection pdf (pada reset password & pin utrade) |  | Martin Haudy | Indri Ariyani | In Progress | Low | 2025-09-15 |  | Pengecekan dari pak Martin S21 | d7a3816e-a486-4a69-a08f-37b081aaacd4
62 | BRD016 | added another Field in Report Client list Part 3 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-14 | 2025-05-23 |  | a23ad192-8939-401f-a0bd-acc1ca2d6b80
63 | BRD017 | Stock position for group with zero balance |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-06-24 | 2025-07-09 |  | 9e9b16bf-850f-4ce9-93ee-e3dc896f55f4
64 | BRD018 | 1. Unlock Mandatory Data pada CIF Maintance 2.Tampilkan Field TIN yang ada di CIF maintance pada client Maintance(Regulator Requirement) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-08-14 | 2025-06-16 |  | 7eeb2f6f-2cc4-4379-960d-0fd064970ed1
65 | BRD019 | Penyesuaian tampilan excel file - contracting: Trade Recapitulation |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-07-24 | 2025-08-04 |  | 0d574422-f6b0-4f26-9887-dc7cc3b669fd
66 | BRD020 | Perubahan Password dan Body Email Institusi Client yang semula ddmmyyClientid menjadi mmyyyyClientID |  | Martin Haudy | Meiliani Intania | Completed | High | 2025-04-24 | 2025-05-30 |  | e9832f1f-7ac6-4013-a473-84d8c6a6adc9
67 | BRD021 | Add "Unit Registry" module (Mutual Fund) In S21 Internal Audit |  | Yoga Dishtira | Jeanny Novianti Cahyadi | Completed | High | 2025-07-18 | 2025-10-27 |  | 62fcc81a-5048-49ad-9a35-b5d73099597f
68 | BRD022 | Operation Purpose and Compliance Request |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-07 | 2025-05-16 |  | 48ff9dc9-1490-40c4-8944-943cd493ea03
69 | BRD023 | Penyesuaian Ajustment ARB 15% Ketentuan bursa tanggal 8 April 2025 |  | David Steven | Indri Ariyani | Completed | High | 2025-04-08 | 2025-04-18 |  | 91f8d76f-1169-42bf-a4a9-53883e3eb4ea
70 | BRD024 | Corporate Action Advice for Merger FREN and EXCL |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-04-22 | 2025-05-02 |  | 7aad4fd7-f7ad-4640-b005-208e01ab99b0
71 | BRD025 | Perubahan Signature pada notification Letter S21 - Notification Closed Account -Notification for change of sales |  | Martin Haudy | Suci Yulianti Ayunita Putri | Completed | High | 2025-04-24 | 2025-05-30 |  | b52bdfa2-7156-4962-bda4-146b3b276f43
72 | BRD026 | Trade Recapitulation By Trade |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-01-02 | 2025-01-08 |  | 250e432b-e55e-450c-afc2-ead31879eb52
73 | BRD027 | BDV Promotion ( - Setting ODT otomatis (Buy Hi Sell Hi) pada client maintenance -field- Day Trade untuk nasabah regular individu online Trading , -Setting Perubahan Data untuk Nasabah Existing regular individu online trading pada client maintenance -field day trade- Buy Hi Sell Hi (list nasabah terlampir) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-02-04 | 2025-02-11 |  | 326cde3a-639f-4238-8f07-ec113b493520
74 | BRD028 | Company Requirement (Modification Client CIF Institutional and individual, additional field all client list, additional field client list Part 1, Modification Search Client (F6) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-17 | 2025-01-22 |  | 20ede8fb-8fe3-4665-afc4-2ebbe053de2e
75 | BRD029 | Penambahan Field Client List "By Created Date" |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-30 | 2025-02-10 |  | 5fa6e9ab-6195-4374-bf98-a0ec7ca5d1b5
76 | BRD030 | 1.Stamping Report DJP 2.Final Income Tax Witholding Report for Stock Sale Transaction |  | Yoga Dishtira | Tjoa Lisa | Completed | High | 2025-02-04 | 2025-02-07 |  | 6fae1e02-36e0-49d4-9870-7b5926a6bebd
77 | BRD031 | Webconsole (mobile) server |  | David Steven | Indri Ariyani | Completed | High | 2025-01-17 | 2025-01-20 |  | 3651c13b-7b81-4063-9ebb-460faec352e5
78 | BRD033 | Report Client Trade Activity |  | Yoga Dishtira | Adelia Haryanto | Completed | High | 2025-02-28 | 2025-04-10 |  | 2e9f42fe-1745-42cb-9f73-0bf415c24ea6
79 | BRD034 | Modify Client List Report |  | Yoga Dishtira | Olivia Penthesilea | Completed | High | 2024-11-11 | 2025-04-10 |  | d4668fec-8386-490b-86d8-247b76965522
80 | BRD035 | 1. Penonaktifkan Program Promo One Day Trade (ODT), Update schema commision tanpa ODT fee, 3. Pembahasan akses Client Commision |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-09-17 | 2025-09-30 |  | 01fabd5f-3b91-452d-8b40-9de3602d9668
81 | BRD036 | Menghilangkan password untuk pdf protection di SOA pada akses web report |  | Martin Haudy | Indri Ariyani | Completed | High | 2025-10-02 | 2025-12-05 | Sudah Naik ke PROD, Konfirmasi ke Tim Ebiz | e9893dc2-20c8-4e74-98ac-02e70a7a9cf6
82 | BRD037 | Update Web banner pada slide 5 dari important Notice Menjadi Utrade New Look |  | David Steven | Indri Ariyani | Completed | High | 2025-10-02 | 2025-10-03 |  | cdca035c-f527-4a77-a1af-386bee581ffd
83 | BRD038 | Penghapusan Profil Ibu Yacinta di website Perusahaan |  | Yoga Dishtira | Indri Ariyani | Completed | High | 2025-10-03 | 2025-10-03 |  | 83afca7a-d7c5-4404-a4de-f61add186c90
84 | BRD040 | Report Statement of Account Report Trade ConfirmationLaporan Transaksi Anggota Bursa (.LTH) , Modify TC Equity Format dan New Format Laporan Transaksi Equity |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-02-24 | 2025-04-09 |  | 9597523d-57f1-44c0-bb15-e91d29efd5d2
85 | BRD041 | Update Website - Banner Change Password |  | David Steven | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-10 |  | 15402600-59eb-449e-9e8e-60f29f796628
86 | BRD042 | Upload Banner UTRADE Apps all device |  | Deni, Eko | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-17 |  | 95b70b65-0147-4234-94c0-49638768fa0d
87 | BRD043 | Menambahkan setting colour untuk tombol order Buy/Sell pada UTRADE Apps |  | Gilang Setiawan, Deni, Dimas | Indri Ariyani | In Progress | High | 2025-10-15 |  | Desktop blum, mobile blum , web sudah tapi blum di masukan setting | a711a593-da1e-4aa5-a491-dd56bd5e4296
88 | BRD044 | Permintaan penyesuian letter pada 1. Utrade account aktivasi di BO terkait password complaxity 2. CMS reset password & PIN |  | David | Indri Ariyani | In Progress | High | 2025-10-07 |  | Sudah Naik ke PROD, menunggu penyesuian dari pak david yang di email ibu Hera baru | deb4757d-7cf1-44d7-a086-03c7952f1bf4
89 | BRD045 | Penambahan Kolom Kekayaan Bersih dan Penghapusan Kolom Asset di CIF Maintenance dan Tarikan Client List |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-10-16 | 2025-12-24 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim CS | 5861d3b5-c2d5-4947-af41-bc65c9c71658
90 | BRD046 | Perubahan email tujuan pelaporan pelanggaran di website Utrade |  | David Steven | Indri Ariyani | Completed |  | 2025-10-14 | 2025-10-23 |  | 7a2f31bd-fa0d-48c5-bc93-dcb8cb3c797f
91 | BRD047 | Perubahan Nomor Rekening Bank untuk Transaksi RDN |  | Yoga Dishtira | Meiliani Intania | Completed |  | 2025-10-22 | 2025-11-08 |  | 1292dd13-5699-4f68-813b-952637717656
92 | BRD048 | Change Mapping MKBD VD 6.6 and update saving balance reconciliation - bank KSEI |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-10-22 | 2025-11-25 |  | f243db5a-073a-4156-91c9-dc5999f460fe
93 | BRD049 | Redirect Website dari kh.co.id ke utrade.co.id |  | David | Indri Ariyani | In Progress | High | 2025-11-27 |  | masih on proggress sudah kirim sertifikat ke singapura dari singapura akan meregister sertifikatnya. | 72b4199b-598a-47c0-8cd7-4e32059d5839
94 | BRD050 | Perubahan Logo UTRADE pada Website dan aplikasi UTRADE (Desktop, Website dan Mobile) |  | David,Gilang,Dimas, Deni | Indri Ariyani | Completed | High | 2025-11-17 | 2025-12-19 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | f2343329-768c-4116-be11-58d333afe403
95 | BRD051 | Perubahan Nama PT Kay Hian Sekuritas pada Website |  | David Steven | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 00000dec-95d8-4fe8-9810-438f3d623bd1
96 | BRD052 | Perubahan Nama PT pada UTRADE all Apps |  | Gilang, Dimas, Deni | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 299e2ed4-083a-48db-84b0-0cf91aa506f3
97 | BRD053 | Migrasi Web Report dan Web Research ke IP Local |  | David | Indri Ariyani | Completed | High | 2025-12-03 |  | Sudah di pindahkan migrasi ke Local webreport dan web research, menunggu Make sure dari tim Ebiz, info update ke david mengenai statusnya (sudah ok atau belum) | 5d710482-4f57-4d42-9bbb-9c4af4f2b0c6
98 | BRD054 | Perubahan nama PT dan Perubahan Logo PT di S21 Remote Trading |  | Nabila | Rizky Saputra | In Progress | High | 2025-12-05 |  | Menunggu update dari Nabila | 8d18f256-b5b6-4dfe-8fd0-754570f04270
99 | BRD055 | Perubahan nama PT dan Perubahan Logo PT di S21 Back Office |  | Yoga Dishtira | Rizky Saputra | Completed | High | 2025-12-17 | 2025-12-22 | Ubah logo manual ke user user yang blum ada logo di S21 BO Semua Divisi | 691eaae2-b881-466a-85a0-a0141de81557
100 | BRD057 | Password Complexity S21 RT |  | Billy | Rizky Saputra | Completed | High | 2025-10-01 | 2025-10-03 |  | 74d718a7-f9eb-40b9-a34a-47a2a83001f0
101 | BRD058 | 1. Unlock Mandatory data pada CIF Maintenance Institutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Sudah di implementasikan di development , Test oleh Tim CS | f13b5136-19fe-4229-aa85-695290da546a
102 | BRD059 | Change Notification Letter |  | Martin Haudy | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Permintaan SP S21Notification dari Tim S21 | 73e57a78-3c3b-453d-818c-9d0af43fb5f2
103 | BRD060 | Menu Watch List Automatic Risk Profile Nasabah Menjadi High Risk CIF Insitutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-12-22 | 2025-12-24 | Sudah di PROD, Menunggu Konfirmasi dari Tim CS | 61d67f87-96b1-4d19-8df3-38e6e5b271f7
104 | BRD02033 | tt4446 |  | gfhfghf | fhfggfgf | In Progress | High | 2025-12-01 |  |  | 30ff57c9-967e-4fce-8bdf-238f2b1ab702
105 | BRD020e | rr | https://id.linkedin.com/learning/ | Martin Haudy | Indriyani | In Progress | High | 2025-12-27 |  |  | 4ac6e532-8a54-4c2e-91bd-d735167f1f96
106 | BRD0203 | reterrt | retet | retet | ertre | New | High |  | 2025-12-27 | rdgtrdgd | 277b8f30-4a6b-4d66-b27d-7486a48c37b9
107 | BRD007 | Project 1 |  |  |  | New | Low | 2025-12-28 |  |  | 7d55179c-3425-4ac3-b7e3-42387bb09c1f
108 | BRD008 | Penambahan Kolom PEP dan Compliance watchlist untuk tarikan list client report |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-08-07 | 2025-08-14 |  | 3b2a9642-d23e-4d43-91d1-d518ea1fe974
109 | BRD009 | Penambahan Report Mutual Fund Unit Registry |  | Chintya | Meiliani Intania | New | High | 2025-09-12 | 2025-10-20 |  | 97b19d0b-550b-4fdc-9139-c39d73fe0333
110 | BRD010 | Perubahan Proses Penyampaian informasi mengenai saham pada papan akselarasi |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | Medium | 2025-04-27 | 2025-05-09 |  | eaeaaacc-afba-4096-802d-06008a8a33f5
111 | BRD011 | Perubahaan Parameter Unusual Transaction Volume |  | Yoga Dishtira | Yandhika Mardi Haposan | Pending | High | 2025-08-12 | 2025-12-22 | Done Bikin UAT dan CR | cdd66ab1-cc6b-4018-a856-1eaf7db50372
112 | BRD012 | Penghapusan Settingan Komisi dengan Skema Daytrade menjadi Nol(0) per Oktober 2025 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Low | 2025-09-15 | 2025-09-30 |  | 9b23a3c4-3cac-4365-b2b0-f2fbbed438f1
113 | BRD013 | Unlock Mandatory Data pada CIF Maintance |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Urgent | 2025-08-14 | 2025-09-30 |  | 3a1cada4-c6cf-46e9-98fb-41d2b6e503ca
114 | BRD014 | 1.Format baru Trade Confirmation 2. Penambahan Stamping Proteksi Password pada Trade Confirmation untuk Product Bond (IPO dan Secondary) 3. Pengaktiffan Realtime Order dan Trade Kembali |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-09-17 | 2025-09-27 |  | 1ee6da81-a17b-4653-8854-3253c2968267
115 | BRD015 | Penyesuaian format passsword protection pdf (pada reset password & pin utrade) |  | Martin Haudy | Indri Ariyani | In Progress | Low | 2025-09-15 |  | Pengecekan dari pak Martin S21 | b9b2b76e-f67a-4403-b5e9-04bb7e89cc61
116 | BRD016 | added another Field in Report Client list Part 3 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-14 | 2025-05-23 |  | 3ea39c3b-a130-4ad1-a8dc-a98437af4972
117 | BRD017 | Stock position for group with zero balance |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-06-24 | 2025-07-09 |  | 4678687f-6314-4697-98e1-436471529ac8
118 | BRD018 | 1. Unlock Mandatory Data pada CIF Maintance 2.Tampilkan Field TIN yang ada di CIF maintance pada client Maintance(Regulator Requirement) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-08-14 | 2025-06-16 |  | 4e8ebf1f-e744-4b80-adcf-0370850a0ecc
119 | BRD019 | Penyesuaian tampilan excel file - contracting: Trade Recapitulation |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-07-24 | 2025-08-04 |  | 3dc5a042-1d4c-4145-be1c-f1223dc4dd59
120 | BRD020 | Perubahan Password dan Body Email Institusi Client yang semula ddmmyyClientid menjadi mmyyyyClientID |  | Martin Haudy | Meiliani Intania | Completed | High | 2025-04-24 | 2025-05-30 |  | 256d00d6-28d5-47ac-aa79-4ec0aeeca3d4
121 | BRD021 | Add "Unit Registry" module (Mutual Fund) In S21 Internal Audit |  | Yoga Dishtira | Jeanny Novianti Cahyadi | Completed | High | 2025-07-18 | 2025-10-27 |  | 8a423500-cd11-4027-91f9-313c23269956
122 | BRD022 | Operation Purpose and Compliance Request |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-07 | 2025-05-16 |  | 73b6de3d-faba-4f26-aea4-3893090e3dc0
123 | BRD023 | Penyesuaian Ajustment ARB 15% Ketentuan bursa tanggal 8 April 2025 |  | David Steven | Indri Ariyani | Completed | High | 2025-04-08 | 2025-04-18 |  | 324bc72d-d6a3-4081-9295-b22edfcd404f
124 | BRD024 | Corporate Action Advice for Merger FREN and EXCL |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-04-22 | 2025-05-02 |  | 3ffb22dc-704d-4d1c-8ade-2b27207ccb8a
125 | BRD025 | Perubahan Signature pada notification Letter S21 - Notification Closed Account -Notification for change of sales |  | Martin Haudy | Suci Yulianti Ayunita Putri | Completed | High | 2025-04-24 | 2025-05-30 |  | 4601d242-2531-4a24-98b5-57c593f0c60f
126 | BRD026 | Trade Recapitulation By Trade |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-01-02 | 2025-01-08 |  | 5553c22e-f332-4fcb-aaa4-fb9843fe242f
127 | BRD027 | BDV Promotion ( - Setting ODT otomatis (Buy Hi Sell Hi) pada client maintenance -field- Day Trade untuk nasabah regular individu online Trading , -Setting Perubahan Data untuk Nasabah Existing regular individu online trading pada client maintenance -field day trade- Buy Hi Sell Hi (list nasabah terlampir) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-02-04 | 2025-02-11 |  | e0ab0e5a-bdcd-4a9c-9eb3-1f25df691d84
128 | BRD028 | Company Requirement (Modification Client CIF Institutional and individual, additional field all client list, additional field client list Part 1, Modification Search Client (F6) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-17 | 2025-01-22 |  | 05abf94b-a3ef-4b4d-93ba-0f0f53fbcc7e
129 | BRD029 | Penambahan Field Client List "By Created Date" |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-30 | 2025-02-10 |  | d4e65efa-bf9b-49b6-99ee-050902478ff7
130 | BRD030 | 1.Stamping Report DJP 2.Final Income Tax Witholding Report for Stock Sale Transaction |  | Yoga Dishtira | Tjoa Lisa | Completed | High | 2025-02-04 | 2025-02-07 |  | f8d23e68-5cc2-4fb0-b4c4-6bd9edc05941
131 | BRD031 | Webconsole (mobile) server |  | David Steven | Indri Ariyani | Completed | High | 2025-01-17 | 2025-01-20 |  | 63975f38-0278-40ce-84b2-587e62858b4a
132 | BRD033 | Report Client Trade Activity |  | Yoga Dishtira | Adelia Haryanto | Completed | High | 2025-02-28 | 2025-04-10 |  | 9dc37cb4-af5d-46b4-bfa7-1e7b5abbac27
133 | BRD034 | Modify Client List Report |  | Yoga Dishtira | Olivia Penthesilea | Completed | High | 2024-11-11 | 2025-04-10 |  | d205e585-54a5-482d-a0dc-6f7e83881378
134 | BRD035 | 1. Penonaktifkan Program Promo One Day Trade (ODT), Update schema commision tanpa ODT fee, 3. Pembahasan akses Client Commision |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-09-17 | 2025-09-30 |  | ae4d4b2d-6531-4ffb-a2da-b9d27f8cf885
135 | BRD036 | Menghilangkan password untuk pdf protection di SOA pada akses web report |  | Martin Haudy | Indri Ariyani | Completed | High | 2025-10-02 | 2025-12-05 | Sudah Naik ke PROD, Konfirmasi ke Tim Ebiz | 77b0e493-1923-4299-bf08-c554f2091ad6
136 | BRD037 | Update Web banner pada slide 5 dari important Notice Menjadi Utrade New Look |  | David Steven | Indri Ariyani | Completed | High | 2025-10-02 | 2025-10-03 |  | 97b2f4bc-4ba0-47a6-8b6e-f9dac021a7b7
137 | BRD038 | Penghapusan Profil Ibu Yacinta di website Perusahaan |  | Yoga Dishtira | Indri Ariyani | Completed | High | 2025-10-03 | 2025-10-03 |  | 5473c2b3-d14e-4954-bb65-53863a6ae4e4
138 | BRD040 | Report Statement of Account Report Trade ConfirmationLaporan Transaksi Anggota Bursa (.LTH) , Modify TC Equity Format dan New Format Laporan Transaksi Equity |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-02-24 | 2025-04-09 |  | 3c2ff4c5-dd4d-46c4-89ac-00019d3f7b55
139 | BRD041 | Update Website - Banner Change Password |  | David Steven | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-10 |  | 3cf705e9-2158-402c-a8d5-99f4f37b967a
140 | BRD042 | Upload Banner UTRADE Apps all device |  | Deni, Eko | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-17 |  | 097ec705-292b-4f9b-82a4-afa89875812f
141 | BRD043 | Menambahkan setting colour untuk tombol order Buy/Sell pada UTRADE Apps |  | Gilang Setiawan, Deni, Dimas | Indri Ariyani | In Progress | High | 2025-10-15 |  | Desktop blum, mobile blum , web sudah tapi blum di masukan setting | 352b9118-5ec3-480d-9d88-bbccc5bd25ab
142 | BRD044 | Permintaan penyesuian letter pada 1. Utrade account aktivasi di BO terkait password complaxity 2. CMS reset password & PIN |  | David | Indri Ariyani | In Progress | High | 2025-10-07 |  | Sudah Naik ke PROD, menunggu penyesuian dari pak david yang di email ibu Hera baru | 17b445ea-bd68-4f77-9ef9-700eb063196d
143 | BRD045 | Penambahan Kolom Kekayaan Bersih dan Penghapusan Kolom Asset di CIF Maintenance dan Tarikan Client List |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-10-16 | 2025-12-24 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim CS | 1dd898e3-6289-44b4-a987-6ffdb16d409b
144 | BRD046 | Perubahan email tujuan pelaporan pelanggaran di website Utrade |  | David Steven | Indri Ariyani | Completed |  | 2025-10-14 | 2025-10-23 |  | 98adbcbe-d8c0-48af-b264-a6a9387a8579
145 | BRD047 | Perubahan Nomor Rekening Bank untuk Transaksi RDN |  | Yoga Dishtira | Meiliani Intania | Completed |  | 2025-10-22 | 2025-11-08 |  | ec4c8c9c-85a5-469a-8d58-e945725d97e1
146 | BRD048 | Change Mapping MKBD VD 6.6 and update saving balance reconciliation - bank KSEI |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-10-22 | 2025-11-25 |  | 8075108f-09c9-4a5c-81dc-071a6719e9c4
147 | BRD049 | Redirect Website dari kh.co.id ke utrade.co.id |  | David | Indri Ariyani | In Progress | High | 2025-11-27 |  | masih on proggress sudah kirim sertifikat ke singapura dari singapura akan meregister sertifikatnya. | 14cbd352-4c2e-4f33-9d18-76031226bf4e
148 | BRD050 | Perubahan Logo UTRADE pada Website dan aplikasi UTRADE (Desktop, Website dan Mobile) |  | David,Gilang,Dimas, Deni | Indri Ariyani | Completed | High | 2025-11-17 | 2025-12-19 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | e7576b2d-ebb4-4f43-98ed-a7328bb9bdea
149 | BRD051 | Perubahan Nama PT Kay Hian Sekuritas pada Website |  | David Steven | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 9aad488b-2536-4035-866e-c7b501318884
150 | BRD052 | Perubahan Nama PT pada UTRADE all Apps |  | Gilang, Dimas, Deni | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 50112072-23db-4e9b-9140-2b56290c7fa9
151 | BRD053 | Migrasi Web Report dan Web Research ke IP Local |  | David | Indri Ariyani | Completed | High | 2025-12-03 |  | Sudah di pindahkan migrasi ke Local webreport dan web research, menunggu Make sure dari tim Ebiz, info update ke david mengenai statusnya (sudah ok atau belum) | e28ae993-cc1e-4c1e-b2b4-ec3e92890b2c
152 | BRD054 | Perubahan nama PT dan Perubahan Logo PT di S21 Remote Trading |  | Nabila | Rizky Saputra | In Progress | High | 2025-12-05 |  | Menunggu update dari Nabila | 94e98831-390d-4b05-91eb-3790d5bca1db
153 | BRD055 | Perubahan nama PT dan Perubahan Logo PT di S21 Back Office |  | Yoga Dishtira | Rizky Saputra | Completed | High | 2025-12-17 | 2025-12-22 | Ubah logo manual ke user user yang blum ada logo di S21 BO Semua Divisi | ab604ecd-564e-4b27-8ab1-a8bd7d1c8ce6
154 | BRD057 | Password Complexity S21 RT |  | Billy | Rizky Saputra | Completed | High | 2025-10-01 | 2025-10-03 |  | fac90b75-eb07-482f-81ca-13a06c7b2a9d
155 | BRD058 | 1. Unlock Mandatory data pada CIF Maintenance Institutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Sudah di implementasikan di development , Test oleh Tim CS | 3fbc3113-c684-408c-b219-4802f4e163e3
156 | BRD059 | Change Notification Letter |  | Martin Haudy | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Permintaan SP S21Notification dari Tim S21 | c5730f3f-7ba0-407f-a068-95345994f37a
157 | BRD060 | Menu Watch List Automatic Risk Profile Nasabah Menjadi High Risk CIF Insitutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-12-22 | 2025-12-24 | Sudah di PROD, Menunggu Konfirmasi dari Tim CS | 601e9182-c4bf-4d15-a9e0-d5836a385454
158 | BRD02033 | tt4446 |  | gfhfghf | fhfggfgf | In Progress | High | 2025-12-01 |  |  | 16704b4b-86ec-486d-95b3-4a168b6c33d2
159 | BRD020e | rr | https://id.linkedin.com/learning/ | Martin Haudy | Indriyani | In Progress | High | 2025-12-27 |  |  | 1bbfe275-a2af-457b-910d-fefcfa3af2ff
160 | BRD0203 | reterrt | retet | retet | ertre | New | High |  | 2025-12-27 | rdgtrdgd | f0cafff0-fb49-4dbe-b9b5-f07893222467