## Sheet1
No | BRD No | Project/Fitur | Link BRD | PIC | Contact Person | Status | Priority | Tanggal Submit | Tanggal Completed | Catatan | uid
1 | BRD010 | Perubahan Proses Penyampaian informasi mengenai saham pada papan akselarasi |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | Medium | 2025-04-27 | 2025-05-09 |  | 6cd4224a-8037-45a5-a78d-5afdea84efad
2 | BRD011 | Perubahaan Parameter Unusual Transaction Volume |  | Yoga Dishtira | Yandhika Mardi Haposan | Pending | High | 2025-08-12 | 2025-12-22 | Done Bikin UAT dan CR | 2eed92d5-312f-4c2a-a319-ac71a8880dfd
3 | BRD012 | Penghapusan Settingan Komisi dengan Skema Daytrade menjadi Nol(0) per Oktober 2025 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Low | 2025-09-15 | 2025-09-30 |  | 112d380d-41e0-4ec7-b585-887b3696caf7
4 | BRD013 | Unlock Mandatory Data pada CIF Maintance |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Urgent | 2025-08-14 | 2025-09-30 |  | 13677cff-c45a-49e7-a05a-982233c69077
5 | BRD014 | 1.Format baru Trade Confirmation 2. Penambahan Stamping Proteksi Password pada Trade Confirmation untuk Product Bond (IPO dan Secondary) 3. Pengaktiffan Realtime Order dan Trade Kembali |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-09-17 | 2025-09-27 |  | ca18844d-6ed1-4c25-b0bb-2d631a7b7136
6 | BRD015 | Penyesuaian format passsword protection pdf (pada reset password & pin utrade) |  | Martin Haudy | Indri Ariyani | In Progress | Low | 2025-09-15 |  | Pengecekan dari pak Martin S21 | 7dea5663-410c-4400-9a08-999698a91747
7 | BRD016 | added another Field in Report Client list Part 3 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-14 | 2025-05-23 |  | 7c11af2f-5458-4270-8c36-2f69ba70d4a4
8 | BRD017 | Stock position for group with zero balance |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-06-24 | 2025-07-09 |  | c573c71d-0d46-46fc-ab92-2712d45aade4
9 | BRD018 | 1. Unlock Mandatory Data pada CIF Maintance 2.Tampilkan Field TIN yang ada di CIF maintance pada client Maintance(Regulator Requirement) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-08-14 | 2025-06-16 |  | 8e03cfe3-3b82-46ff-9351-5590c0858cf9
10 | BRD019 | Penyesuaian tampilan excel file - contracting: Trade Recapitulation |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-07-24 | 2025-08-04 |  | 8fa7b82a-0737-4719-8b76-cc0600a606d1
11 | BRD020 | Perubahan Password dan Body Email Institusi Client yang semula ddmmyyClientid menjadi mmyyyyClientID |  | Martin Haudy | Meiliani Intania | Completed | High | 2025-04-24 | 2025-05-30 |  | a4c3963c-e91f-479c-b27b-b423134a72dd
12 | BRD021 | Add "Unit Registry" module (Mutual Fund) In S21 Internal Audit |  | Yoga Dishtira | Jeanny Novianti Cahyadi | Completed | High | 2025-07-18 | 2025-10-27 |  | e0d4eb02-9287-47fb-a9e0-7bcf756d04df
13 | BRD022 | Operation Purpose and Compliance Request |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-07 | 2025-05-16 |  | 129879b6-85d0-4e4b-978f-ff2383b96eac
14 | BRD023 | Penyesuaian Ajustment ARB 15% Ketentuan bursa tanggal 8 April 2025 |  | David Steven | Indri Ariyani | Completed | High | 2025-04-08 | 2025-04-18 |  | 204f72e1-53d2-4b1d-895e-ff4a29350361
15 | BRD024 | Corporate Action Advice for Merger FREN and EXCL |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-04-22 | 2025-05-02 |  | 9720c524-7efe-40f8-aaf3-68d5369f7087
16 | BRD025 | Perubahan Signature pada notification Letter S21 - Notification Closed Account -Notification for change of sales |  | Martin Haudy | Suci Yulianti Ayunita Putri | Completed | High | 2025-04-24 | 2025-05-30 |  | 996d412a-dbb7-4ebc-a9cc-7227cec575e1
17 | BRD026 | Trade Recapitulation By Trade |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-01-02 | 2025-01-08 |  | 7a816769-a4c1-4be3-8b1e-db6fcd37f853
18 | BRD027 | BDV Promotion ( - Setting ODT otomatis (Buy Hi Sell Hi) pada client maintenance -field- Day Trade untuk nasabah regular individu online Trading , -Setting Perubahan Data untuk Nasabah Existing regular individu online trading pada client maintenance -field day trade- Buy Hi Sell Hi (list nasabah terlampir) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-02-04 | 2025-02-11 |  | c5ffa0a1-3010-4152-91bf-59a9efe820b4
19 | BRD028 | Company Requirement (Modification Client CIF Institutional and individual, additional field all client list, additional field client list Part 1, Modification Search Client (F6) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-17 | 2025-01-22 |  | b251412a-66bc-4e4f-b7fa-0d36dd72fa1d
20 | BRD029 | Penambahan Field Client List "By Created Date" |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-30 | 2025-02-10 |  | ede04858-71a6-47be-b021-6edd26cea457
21 | BRD030 | 1.Stamping Report DJP 2.Final Income Tax Witholding Report for Stock Sale Transaction |  | Yoga Dishtira | Tjoa Lisa | Completed | High | 2025-02-04 | 2025-02-07 |  | 34cc5de9-8463-40e5-8783-5fee2b26e0ae
22 | BRD031 | Webconsole (mobile) server |  | David Steven | Indri Ariyani | Completed | High | 2025-01-17 | 2025-01-20 |  | dbe18547-e4c9-43bd-8443-4ef998f1e332
23 | BRD033 | Report Client Trade Activity |  | Yoga Dishtira | Adelia Haryanto | Completed | High | 2025-02-28 | 2025-04-10 |  | 942aadfb-4b40-42bf-9aa9-d8f09a0b61ce
24 | BRD034 | Modify Client List Report |  | Yoga Dishtira | Olivia Penthesilea | Completed | High | 2024-11-11 | 2025-04-10 |  | 305f05c5-4e09-40df-9d56-fe8ab00ba090
25 | BRD035 | 1. Penonaktifkan Program Promo One Day Trade (ODT), Update schema commision tanpa ODT fee, 3. Pembahasan akses Client Commision |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-09-17 | 2025-09-30 |  | eee08513-802f-426f-858f-cdc8b3179012
26 | BRD036 | Menghilangkan password untuk pdf protection di SOA pada akses web report |  | Martin Haudy | Indri Ariyani | Completed | High | 2025-10-02 | 2025-12-05 | Sudah Naik ke PROD, Konfirmasi ke Tim Ebiz | f9b3f717-f940-4341-88f8-e2e93cf0a4d5
27 | BRD037 | Update Web banner pada slide 5 dari important Notice Menjadi Utrade New Look |  | David Steven | Indri Ariyani | Completed | High | 2025-10-02 | 2025-10-03 |  | 5d387e9c-1dfd-4811-a917-fe8e65f52787
28 | BRD038 | Penghapusan Profil Ibu Yacinta di website Perusahaan |  | Yoga Dishtira | Indri Ariyani | Completed | High | 2025-10-03 | 2025-10-03 |  | 9d06b2d1-1b4c-49f3-bdc3-cb40423dfbc2
29 | BRD040 | Report Statement of Account Report Trade ConfirmationLaporan Transaksi Anggota Bursa (.LTH) , Modify TC Equity Format dan New Format Laporan Transaksi Equity |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-02-24 | 2025-04-09 |  | dc3894d7-e4b8-4f20-b640-10dbb6d335fd
30 | BRD041 | Update Website - Banner Change Password |  | David Steven | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-10 |  | abe7660e-e364-4209-9f2e-9b7ece19b128
31 | BRD043 | Menambahkan setting colour untuk tombol order Buy/Sell pada UTRADE Apps |  | Gilang Setiawan, Deni, Dimas | Indri Ariyani | In Progress | High | 2025-10-15 |  | Desktop blum, mobile blum , web sudah tapi blum di masukan setting | 58022197-db44-4a32-b821-b3fbeb55da48
32 | BRD044 | Permintaan penyesuian letter pada 1. Utrade account aktivasi di BO terkait password complaxity 2. CMS reset password & PIN |  | David | Indri Ariyani | In Progress | High | 2025-10-07 |  | Sudah Naik ke PROD, menunggu penyesuian dari pak david yang di email ibu Hera baru | 56db3194-c99a-454c-b0c6-e15c4f785ed8
33 | BRD045 | Penambahan Kolom Kekayaan Bersih dan Penghapusan Kolom Asset di CIF Maintenance dan Tarikan Client List |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-10-16 | 2025-12-24 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim CS | 8cfb3ad8-68a3-4161-9707-0ad38ebc8951
34 | BRD046 | Perubahan email tujuan pelaporan pelanggaran di website Utrade |  | David Steven | Indri Ariyani | Completed |  | 2025-10-14 | 2025-10-23 |  | 920615eb-e9c5-4ea5-8c9f-f202034886d2
35 | BRD047 | Perubahan Nomor Rekening Bank untuk Transaksi RDN |  | Yoga Dishtira | Meiliani Intania | Completed |  | 2025-10-22 | 2025-11-08 |  | ca5603d2-ef3e-48ca-ba0e-0c6ce423be43
36 | BRD048 | Change Mapping MKBD VD 6.6 and update saving balance reconciliation - bank KSEI |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-10-22 | 2025-11-25 |  | a167ead5-6399-44c6-b7a4-f3fedfa5cc1a
37 | BRD049 | Redirect Website dari kh.co.id ke utrade.co.id |  | David | Indri Ariyani | In Progress | High | 2025-11-27 |  | masih on proggress sudah kirim sertifikat ke singapura dari singapura akan meregister sertifikatnya. | 06e78614-1e0b-4001-8abf-117a2b695841
38 | BRD050 | Perubahan Logo UTRADE pada Website dan aplikasi UTRADE (Desktop, Website dan Mobile) |  | David,Gilang,Dimas, Deni | Indri Ariyani | Completed | High | 2025-11-17 | 2025-12-19 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | a2881395-382a-4f48-8e83-1b6b98f66ed1
39 | BRD051 | Perubahan Nama PT Kay Hian Sekuritas pada Website |  | David Steven | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | d1815773-4f84-472e-ab40-4ea805b9c9cc
40 | BRD052 | Perubahan Nama PT pada UTRADE all Apps |  | Gilang, Dimas, Deni | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 474452e2-cf64-4e61-a1e1-f3ff652a463c
41 | BRD053 | Migrasi Web Report dan Web Research ke IP Local |  | David | Indri Ariyani | Completed | High | 2025-12-03 |  | Sudah di pindahkan migrasi ke Local webreport dan web research, menunggu Make sure dari tim Ebiz, info update ke david mengenai statusnya (sudah ok atau belum) | 002badf2-3e62-43b0-8bcf-b04f26095528
42 | BRD054 | Perubahan nama PT dan Perubahan Logo PT di S21 Remote Trading |  | Nabila | Rizky Saputra | In Progress | High | 2025-12-05 |  | Menunggu update dari Nabila | efe6a2b2-4d2a-4e33-a0c5-0b14a954933d
43 | BRD055 | Perubahan nama PT dan Perubahan Logo PT di S21 Back Office |  | Yoga Dishtira | Rizky Saputra | Completed | High | 2025-12-17 | 2025-12-22 | Ubah logo manual ke user user yang blum ada logo di S21 BO Semua Divisi | 2cdc6cbd-fc33-4785-b25b-1572fa9f6ca5
44 | BRD057 | Password Complexity S21 RT |  | Billy | Rizky Saputra | Completed | High | 2025-10-01 | 2025-10-03 |  | 00939a84-416f-4500-bc65-4f54ca6bc218
45 | BRD058 | 1. Unlock Mandatory data pada CIF Maintenance Institutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Sudah di implementasikan di development , Test oleh Tim CS | c0f0a71b-8e66-4f51-9eea-9a477ace13f4
46 | BRD059 | Change Notification Letter |  | Martin Haudy | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Permintaan SP S21Notification dari Tim S21 | 042775f3-f36b-4a51-9998-6bae49b1aab2
47 | BRD060 | Menu Watch List Automatic Risk Profile Nasabah Menjadi High Risk CIF Insitutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-12-22 | 2025-12-24 | Sudah di PROD, Menunggu Konfirmasi dari Tim CS | e375f91d-ec2d-45cc-a0dc-7c20f20fcefd
48 | BRD02033 | tt4446 |  | gfhfghf | fhfggfgf | In Progress | High | 2025-12-01 |  |  | 0acafd93-967b-49ec-b88b-1775e5e4e389
49 | BRD020e | rr | https://id.linkedin.com/learning/ | Martin Haudy | Indriyani | In Progress | High | 2025-12-27 |  |  | 9df13d32-a90a-4842-807d-5ab0f27f7a65
50 | BRD0203 | reterrt | retet | retet | ertre | New | High |  | 2025-12-27 | rdgtrdgd | 9fd3a479-9f3a-4be6-96d1-1e12e0c1ae9d
51 | BRD008 | Penambahan Kolom PEP dan Compliance watchlist untuk tarikan list client report |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-08-07 | 2025-08-14 |  | d4d27a7c-7990-4ce4-9722-e3daca9d002f
52 | BRD009 | Penambahan Report Mutual Fund Unit Registry |  | Chintya | Meiliani Intania | New | High | 2025-09-12 | 2025-10-20 |  | 45ed3ede-4318-445e-91de-54b13b007cad
53 | BRD010 | Perubahan Proses Penyampaian informasi mengenai saham pada papan akselarasi |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | Medium | 2025-04-27 | 2025-05-09 |  | 8a7cae12-4fbf-4b1b-b548-3023e514428a
54 | BRD011 | Perubahaan Parameter Unusual Transaction Volume |  | Yoga Dishtira | Yandhika Mardi Haposan | Pending | High | 2025-08-12 | 2025-12-22 | Done Bikin UAT dan CR | a27d28bf-1ea8-4bea-8bc8-9305ba5803e2
55 | BRD012 | Penghapusan Settingan Komisi dengan Skema Daytrade menjadi Nol(0) per Oktober 2025 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Low | 2025-09-15 | 2025-09-30 |  | 1394ecec-5b79-4b67-b8af-13160fc59df9
56 | BRD013 | Unlock Mandatory Data pada CIF Maintance |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | Urgent | 2025-08-14 | 2025-09-30 |  | 61c60559-e82b-40f9-bc1a-2fc6e1717a38
57 | BRD014 | 1.Format baru Trade Confirmation 2. Penambahan Stamping Proteksi Password pada Trade Confirmation untuk Product Bond (IPO dan Secondary) 3. Pengaktiffan Realtime Order dan Trade Kembali |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-09-17 | 2025-09-27 |  | d7d6dbac-3478-46e6-81ee-f9f7d49c1885
58 | BRD015 | Penyesuaian format passsword protection pdf (pada reset password & pin utrade) |  | Martin Haudy | Indri Ariyani | In Progress | Low | 2025-09-15 |  | Pengecekan dari pak Martin S21 | 85dee200-5826-459f-b76a-51f8c471ae06
59 | BRD016 | added another Field in Report Client list Part 3 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-14 | 2025-05-23 |  | 6807f634-3338-428e-970f-827348c524f6
60 | BRD017 | Stock position for group with zero balance |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-06-24 | 2025-07-09 |  | a5055c7a-d750-48ec-a44e-9d07e54bc666
61 | BRD018 | 1. Unlock Mandatory Data pada CIF Maintance 2.Tampilkan Field TIN yang ada di CIF maintance pada client Maintance(Regulator Requirement) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-08-14 | 2025-06-16 |  | 39f36029-9f6e-4d64-85ee-080d6c4e2a8f
62 | BRD019 | Penyesuaian tampilan excel file - contracting: Trade Recapitulation |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-07-24 | 2025-08-04 |  | 709cc924-394f-414d-88ab-198b16c2bcef
63 | BRD020 | Perubahan Password dan Body Email Institusi Client yang semula ddmmyyClientid menjadi mmyyyyClientID |  | Martin Haudy | Meiliani Intania | Completed | High | 2025-04-24 | 2025-05-30 |  | 02af8cbb-b290-48a3-8356-58759611d879
64 | BRD021 | Add "Unit Registry" module (Mutual Fund) In S21 Internal Audit |  | Yoga Dishtira | Jeanny Novianti Cahyadi | Completed | High | 2025-07-18 | 2025-10-27 |  | 06373037-62b3-4d00-a7c5-1153a46520bc
65 | BRD022 | Operation Purpose and Compliance Request |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-07 | 2025-05-16 |  | 6c68ea64-dbc8-494e-9768-226f1e4c244d
66 | BRD023 | Penyesuaian Ajustment ARB 15% Ketentuan bursa tanggal 8 April 2025 |  | David Steven | Indri Ariyani | Completed | High | 2025-04-08 | 2025-04-18 |  | 13e330be-75d5-4c0b-b270-7b0fc48f91cf
67 | BRD024 | Corporate Action Advice for Merger FREN and EXCL |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-04-22 | 2025-05-02 |  | 08ca510c-858f-4342-818a-3ab2294b1c70
68 | BRD025 | Perubahan Signature pada notification Letter S21 - Notification Closed Account -Notification for change of sales |  | Martin Haudy | Suci Yulianti Ayunita Putri | Completed | High | 2025-04-24 | 2025-05-30 |  | 25ab45b4-cd20-49b2-aadb-d282aba6ee20
69 | BRD026 | Trade Recapitulation By Trade |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-01-02 | 2025-01-08 |  | 29e8f852-f4ce-49c5-a40a-84de4df1b4da
70 | BRD027 | BDV Promotion ( - Setting ODT otomatis (Buy Hi Sell Hi) pada client maintenance -field- Day Trade untuk nasabah regular individu online Trading , -Setting Perubahan Data untuk Nasabah Existing regular individu online trading pada client maintenance -field day trade- Buy Hi Sell Hi (list nasabah terlampir) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-02-04 | 2025-02-11 |  | 6b06a48e-9360-4798-9629-c3eec11d64c1
71 | BRD028 | Company Requirement (Modification Client CIF Institutional and individual, additional field all client list, additional field client list Part 1, Modification Search Client (F6) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-17 | 2025-01-22 |  | 7e507fde-44a1-45b0-97f6-d83619910233
72 | BRD029 | Penambahan Field Client List "By Created Date" |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-30 | 2025-02-10 |  | e111c9b4-962d-45b7-bcde-ec312a9af407
73 | BRD030 | 1.Stamping Report DJP 2.Final Income Tax Witholding Report for Stock Sale Transaction |  | Yoga Dishtira | Tjoa Lisa | Completed | High | 2025-02-04 | 2025-02-07 |  | 450627c8-ff6a-46ec-9a06-b652e1b4a954
74 | BRD031 | Webconsole (mobile) server |  | David Steven | Indri Ariyani | Completed | High | 2025-01-17 | 2025-01-20 |  | 60f306f2-7ede-4d4c-84ee-514cdb1aa663
75 | BRD033 | Report Client Trade Activity |  | Yoga Dishtira | Adelia Haryanto | Completed | High | 2025-02-28 | 2025-04-10 |  | 1d3767b9-8f1c-4eda-90f6-7b9a74d187c6
76 | BRD034 | Modify Client List Report |  | Yoga Dishtira | Olivia Penthesilea | Completed | High | 2024-11-11 | 2025-04-10 |  | 3603865a-72b1-48d9-8d09-7e4ddb442716
77 | BRD035 | 1. Penonaktifkan Program Promo One Day Trade (ODT), Update schema commision tanpa ODT fee, 3. Pembahasan akses Client Commision |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-09-17 | 2025-09-30 |  | 306be4e0-aa4b-44cd-a245-a2c8e9f7530f
78 | BRD036 | Menghilangkan password untuk pdf protection di SOA pada akses web report |  | Martin Haudy | Indri Ariyani | Completed | High | 2025-10-02 | 2025-12-05 | Sudah Naik ke PROD, Konfirmasi ke Tim Ebiz | 0ffd4623-1fb5-4ae2-bbd7-aa180d16790a
79 | BRD037 | Update Web banner pada slide 5 dari important Notice Menjadi Utrade New Look |  | David Steven | Indri Ariyani | Completed | High | 2025-10-02 | 2025-10-03 |  | 463b2871-86af-4479-a13e-5dd8dd9618d6
80 | BRD038 | Penghapusan Profil Ibu Yacinta di website Perusahaan |  | Yoga Dishtira | Indri Ariyani | Completed | High | 2025-10-03 | 2025-10-03 |  | 588de316-6fe7-4b61-8193-7a94c3aefc79
81 | BRD040 | Report Statement of Account Report Trade ConfirmationLaporan Transaksi Anggota Bursa (.LTH) , Modify TC Equity Format dan New Format Laporan Transaksi Equity |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-02-24 | 2025-04-09 |  | 267c5686-a4a2-4348-bd2a-85cfcdd95831
82 | BRD041 | Update Website - Banner Change Password |  | David Steven | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-10 |  | 63d3ca52-c820-49ac-8c7a-a84ed05a69a0
83 | BRD042 | Upload Banner UTRADE Apps all device |  | Deni, Eko | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-17 |  | 7a3d494c-3f47-4743-b89c-547738c8caad
84 | BRD043 | Menambahkan setting colour untuk tombol order Buy/Sell pada UTRADE Apps |  | Gilang Setiawan, Deni, Dimas | Indri Ariyani | In Progress | High | 2025-10-15 |  | Desktop blum, mobile blum , web sudah tapi blum di masukan setting | 75359b5e-d63b-4f5f-a31b-56aed60805e1
85 | BRD044 | Permintaan penyesuian letter pada 1. Utrade account aktivasi di BO terkait password complaxity 2. CMS reset password & PIN |  | David | Indri Ariyani | In Progress | High | 2025-10-07 |  | Sudah Naik ke PROD, menunggu penyesuian dari pak david yang di email ibu Hera baru | dc672060-30e8-47f2-8b93-f6535117c15e
86 | BRD045 | Penambahan Kolom Kekayaan Bersih dan Penghapusan Kolom Asset di CIF Maintenance dan Tarikan Client List |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-10-16 | 2025-12-24 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim CS | 29209f7e-5e12-4f3e-be7f-086c230cf360
87 | BRD046 | Perubahan email tujuan pelaporan pelanggaran di website Utrade |  | David Steven | Indri Ariyani | Completed |  | 2025-10-14 | 2025-10-23 |  | c9e1317c-fee9-43b5-af5d-29b4a871682e
88 | BRD047 | Perubahan Nomor Rekening Bank untuk Transaksi RDN |  | Yoga Dishtira | Meiliani Intania | Completed |  | 2025-10-22 | 2025-11-08 |  | b0333c59-e125-465e-820b-778979c08d17
89 | BRD048 | Change Mapping MKBD VD 6.6 and update saving balance reconciliation - bank KSEI |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-10-22 | 2025-11-25 |  | ecc16f27-d1e8-4899-b22e-64f9a2685b83
90 | BRD049 | Redirect Website dari kh.co.id ke utrade.co.id |  | David | Indri Ariyani | In Progress | High | 2025-11-27 |  | masih on proggress sudah kirim sertifikat ke singapura dari singapura akan meregister sertifikatnya. | a5c3e89a-6dc8-4fbe-bdf8-a5ec87f75228
91 | BRD050 | Perubahan Logo UTRADE pada Website dan aplikasi UTRADE (Desktop, Website dan Mobile) |  | David,Gilang,Dimas, Deni | Indri Ariyani | Completed | High | 2025-11-17 | 2025-12-19 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 5ec4091c-0dd3-4ef4-add2-5b3c56886148
92 | BRD051 | Perubahan Nama PT Kay Hian Sekuritas pada Website |  | David Steven | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | b345bc1e-c22c-4342-a0de-b6b37ce7005c
93 | BRD052 | Perubahan Nama PT pada UTRADE all Apps |  | Gilang, Dimas, Deni | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | 10ec78d7-c011-45ee-a618-af91ccdd9e09
94 | BRD053 | Migrasi Web Report dan Web Research ke IP Local |  | David | Indri Ariyani | Completed | High | 2025-12-03 |  | Sudah di pindahkan migrasi ke Local webreport dan web research, menunggu Make sure dari tim Ebiz, info update ke david mengenai statusnya (sudah ok atau belum) | 17141900-07dc-4eae-8ddf-889cbf5738cd
95 | BRD054 | Perubahan nama PT dan Perubahan Logo PT di S21 Remote Trading |  | Nabila | Rizky Saputra | In Progress | High | 2025-12-05 |  | Menunggu update dari Nabila | f9780641-b0d7-45c1-bbe3-dd4a6aff11ef
96 | BRD055 | Perubahan nama PT dan Perubahan Logo PT di S21 Back Office |  | Yoga Dishtira | Rizky Saputra | Completed | High | 2025-12-17 | 2025-12-22 | Ubah logo manual ke user user yang blum ada logo di S21 BO Semua Divisi | bf77a496-64f0-47be-87c8-1c9fcc344d82
97 | BRD057 | Password Complexity S21 RT |  | Billy | Rizky Saputra | Completed | High | 2025-10-01 | 2025-10-03 |  | 94e2d11e-f39f-4fb5-b72d-179bf08d2655
98 | BRD058 | 1. Unlock Mandatory data pada CIF Maintenance Institutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Sudah di implementasikan di development , Test oleh Tim CS | b6cf4a19-c13c-4a1e-9479-506fe565798b
99 | BRD059 | Change Notification Letter |  | Martin Haudy | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Permintaan SP S21Notification dari Tim S21 | 8ff4a352-e1bd-4fc7-9a04-18abb15fdc59
100 | BRD060 | Menu Watch List Automatic Risk Profile Nasabah Menjadi High Risk CIF Insitutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-12-22 | 2025-12-24 | Sudah di PROD, Menunggu Konfirmasi dari Tim CS | 01b148df-17f9-4e73-ac6f-ec45c03e1e28
101 | BRD02033 | tt4446 |  | gfhfghf | fhfggfgf | In Progress | High | 2025-12-01 |  |  | 8fcdc507-0d20-4773-8f9d-a6d2a90eb368
102 | BRD020e | rr | https://id.linkedin.com/learning/ | Martin Haudy | Indriyani | In Progress | High | 2025-12-27 |  |  | b17aaf5e-535a-4674-87e7-8f8ac8e6ac0e
103 | BRD0203 | reterrt | retet | retet | ertre | New | High |  | 2025-12-27 | rdgtrdgd | 6b4a4530-eaa7-4318-b335-040100b31336
104 | BRD0074 | Project 1 | 1 |  |  | New | Medium | 2025-12-28 |  | test | 089ef987-54cb-4d6f-a8af-29f619c478f3