## Sheet1
No | BRD No | Project/Fitur | Link BRD | PIC | Contact Person | Status | Priority | Tanggal Submit | Tanggal Completed | Catatan | uid
1 | BRD001 | Penambahan Dokumen Perjanjian Rekening Efek dan Ketentuan Pelindungan Data Pribadi |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-07-11 | 2025-07-14 | Done Bikin UAT dan CR | b56969df-5898-4e15-8b4e-84d2fa7ebc5a
2 | BRD002 | Additional View Mode TC Equity (Sending Trade Settlement) |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-02-28 | 2025-03-21 |  | 1d5b8a0a-520b-4e5a-b1b3-2131d220e29a
3 | BRD004 | List of Fixed Assets |  | Yoga Dishtira | Tjoa Lisa | Completed | High | 2025-02-28 | 2025-03-21 |  | b46cca70-53b1-4bd2-9dbd-009708f39b3b
4 | BRD005 | Update Web Banner hari raya Nyepi dan Hari Raya idul Fitri |  | David Seven | Indri Ariyani | Completed | High | 2025-03-26 | 2025-03-28 |  | 9bd9517f-f6c5-4667-a624-8fab6d283ee7
5 | BRD006 | Modification request : create new page - utrade.co.id |  | David Steven | Indri Ariyani | Completed | High | 2025-03-10 | 2025-03-14 |  | f4fc9f95-7ef2-4aa4-b57a-4ce712b54e5e
6 | BRD007 | Menambahkan link berisi dokumen perjanjian pembukaan rekening efek dan kebijakan perlindungan data pribadi pada TC |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-09-08 | 2025-09-19 |  | ea86fc46-2178-4bc4-b472-e3c47f06884f
7 | BRD008 | Penambahan Kolom PEP dan Compliance watchlist untuk tarikan list client report |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-08-07 | 2025-08-14 |  | 583a6b48-5d06-49c8-b386-64d04529c599
8 | BRD009 | Penambahan Report Mutual Fund Unit Registry |  | Chintya | Meiliani Intania | Completed | High | 2025-09-12 | 2025-10-20 |  | 68e3ff55-da4a-4250-afed-d0ba7a0d4a12
9 | BRD010 | Perubahan Proses Penyampaian informasi mengenai saham pada papan akselarasi |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-04-27 | 2025-05-09 |  | c3241852-59c4-4b80-ab9c-7be89c632ce8
10 | BRD011 | Perubahaan Parameter Unusual Transaction Volume |  | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-08-12 | 2025-12-22 | Done Bikin UAT dan CR | e920d13d-ed43-4cad-9ea5-d386cdf53d69
11 | BRD012 | Penghapusan Settingan Komisi dengan Skema Daytrade menjadi Nol(0) per Oktober 2025 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-09-15 | 2025-09-30 |  | 3a9a300e-fbbf-4378-8562-0b53a733077f
12 | BRD013 | Unlock Mandatory Data pada CIF Maintance |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-08-14 | 2025-09-30 |  | 4433b299-8fba-45b6-b5ce-c7592cc84c5f
13 | BRD014 | 1.Format baru Trade Confirmation 2. Penambahan Stamping Proteksi Password pada Trade Confirmation untuk Product Bond (IPO dan Secondary) 3. Pengaktiffan Realtime Order dan Trade Kembali |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-09-17 | 2025-09-27 |  | 964cc09c-c29b-4cbb-be54-58706463519c
14 | BRD015 | Penyesuaian format passsword protection pdf (pada reset password & pin utrade) |  | Martin Haudy | Indri Ariyani | In Progress | High | 2025-09-15 |  | saat ini kami sedang melakukan follow-up kembali dengan tim Report Gateway | fe29c461-a44b-4778-861b-c691886789a4
15 | BRD016 | added another Field in Report Client list Part 3 |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-14 | 2025-05-23 |  | e7168637-a0b6-4df7-b482-f73dca2cd3dd
16 | BRD017 | Stock position for group with zero balance |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-06-24 | 2025-07-09 |  | 745995f8-d94d-4be1-adfc-f401a1e458eb
17 | BRD018 | 1. Unlock Mandatory Data pada CIF Maintance 2.Tampilkan Field TIN yang ada di CIF maintance pada client Maintance(Regulator Requirement) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-08-14 | 2025-06-16 |  | 5678c7fb-28f5-42d5-b49e-e9057dd0b5c2
18 | BRD019 | Penyesuaian tampilan excel file - contracting: Trade Recapitulation |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-07-24 | 2025-08-04 |  | 339c3ab5-3c44-4330-b60d-e7e2e2bf7e3b
19 | BRD020 | Perubahan Password dan Body Email Institusi Client yang semula ddmmyyClientid menjadi mmyyyyClientID |  | Martin Haudy | Meiliani Intania | Completed | High | 2025-04-24 | 2025-05-30 |  | c249fd65-4cc0-4879-ac46-a1ad1bd6e884
20 | BRD021 | Add "Unit Registry" module (Mutual Fund) In S21 Internal Audit |  | Yoga Dishtira | Jeanny Novianti Cahyadi | Completed | High | 2025-07-18 | 2025-10-27 |  | 3aa4e789-d74e-48af-8bf3-4e1541c56a85
21 | BRD022 | Operation Purpose and Compliance Request |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-05-07 | 2025-05-16 |  | 58e27cb3-ca64-41a7-a56a-e28c1ecd6123
22 | BRD023 | Penyesuaian Ajustment ARB 15% Ketentuan bursa tanggal 8 April 2025 |  | David Steven | Indri Ariyani | Completed | High | 2025-04-08 | 2025-04-18 |  | e2c3d660-524d-49fe-bf72-7555f91f02e9
23 | BRD024 | Corporate Action Advice for Merger FREN and EXCL |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-04-22 | 2025-05-02 |  | 6ab2fc54-6120-4c3e-a313-cf6381292206
24 | BRD025 | Perubahan Signature pada notification Letter S21 - Notification Closed Account -Notification for change of sales |  | Martin Haudy | Suci Yulianti Ayunita Putri | Completed | High | 2025-04-24 | 2025-05-30 |  | 28f2d6ec-8d08-4112-83ae-c78af08008aa
25 | BRD026 | Trade Recapitulation By Trade |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-01-02 | 2025-01-08 |  | ee2b779d-6b6f-466c-b0da-286c6fea6df5
26 | BRD027 | BDV Promotion ( - Setting ODT otomatis (Buy Hi Sell Hi) pada client maintenance -field- Day Trade untuk nasabah regular individu online Trading , -Setting Perubahan Data untuk Nasabah Existing regular individu online trading pada client maintenance -field day trade- Buy Hi Sell Hi (list nasabah terlampir) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-02-04 | 2025-02-11 |  | 9e9ff204-d6a0-4445-9553-c717a99379d6
27 | BRD028 | Company Requirement (Modification Client CIF Institutional and individual, additional field all client list, additional field client list Part 1, Modification Search Client (F6) |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-17 | 2025-01-22 |  | ee4c9c97-ded4-4036-ad38-1d5c6005c7bc
28 | BRD029 | Penambahan Field Client List "By Created Date" |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-01-30 | 2025-02-10 |  | 90d0f091-69c4-400c-a5f1-39362fbfd1bd
29 | BRD030 | 1.Stamping Report DJP 2.Final Income Tax Witholding Report for Stock Sale Transaction |  | Yoga Dishtira | Tjoa Lisa | Completed | High | 2025-02-04 | 2025-02-07 |  | 0d405084-0ae2-4fd5-8ba6-81f9341f1358
30 | BRD031 | Webconsole (mobile) server |  | David Steven | Indri Ariyani | Completed | High | 2025-01-17 | 2025-01-20 |  | 2309fa01-c040-42d6-bb97-6c49e5319b9e
31 | BRD033 | Report Client Trade Activity |  | Yoga Dishtira | Adelia Haryanto | Completed | High | 2025-02-28 | 2025-04-10 |  | 1a44e99d-8c06-455a-bd5f-c410f75dc5df
32 | BRD034 | Modify Client List Report |  | Yoga Dishtira | Olivia Penthesilea | Completed | High | 2024-11-11 | 2025-04-10 |  | fea4ea57-52a4-44aa-bafd-dce79b1f666b
33 | BRD035 | 1. Penonaktifkan Program Promo One Day Trade (ODT), Update schema commision tanpa ODT fee, 3. Pembahasan akses Client Commision |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-09-17 | 2025-09-30 |  | b3441ccf-2c20-43ed-997c-840e9c34350f
34 | BRD036 | Menghilangkan password untuk pdf protection di SOA pada akses web report | https://url-shortener.me/5L49 | Martin Haudy | Indri Ariyani | Completed | High | 2025-10-02 | 2025-12-05 | Done Bikin UAT dan CR | cb73487e-f80d-4745-9f81-12c89f2ce520
35 | BRD037 | Update Web banner pada slide 5 dari important Notice Menjadi Utrade New Look |  | David Steven | Indri Ariyani | Completed | High | 2025-10-02 | 2025-10-03 |  | f93c53ca-2ae1-48ca-b054-c40499ee466a
36 | BRD038 | Penghapusan Profil Ibu Yacinta di website Perusahaan |  | Yoga Dishtira | Indri Ariyani | Completed | High | 2025-10-03 | 2025-10-03 |  | a353ae8e-abac-48da-a5af-e63e8e53364e
37 | BRD040 | Report Statement of Account Report Trade ConfirmationLaporan Transaksi Anggota Bursa (.LTH) , Modify TC Equity Format dan New Format Laporan Transaksi Equity |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-02-24 | 2025-04-09 |  | 48171434-1313-45f7-b73a-bcc7ca706762
38 | BRD041 | Update Website - Banner Change Password |  | David Steven | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-10 |  | 160331b5-dd4a-4383-b096-f74d9c7be2a4
39 | BRD042 | Upload Banner UTRADE Apps all device |  | Deni, Eko | Indri Ariyani | Completed | High | 2025-10-08 | 2025-10-17 |  | dd5bda49-6fd1-46ac-aa43-c397b49fd19b
40 | BRD043 | Menambahkan setting colour untuk tombol order Buy/Sell pada UTRADE Apps | https://url-shortener.me/5L8K | Gilang Setiawan, Deni, Dimas | Indri Ariyani | In Progress | High | 2025-10-15 |  | •Mobile sudah di sent Pak Gilang untuk di test ebiz di area dev •Dekstop update apps akan di pisah dg 2FA, estimasi apps akan di kirim dimas Rabu depan, 14 Jan •Web Estimasi apps akan di kirim dimas Rabu depan, 14 Jan | 7c840833-9492-4326-9217-8c577a51c4a8
41 | BRD044 | Permintaan penyesuian letter pada 1. Utrade account aktivasi di BO terkait password complaxity 2. CMS reset password & PIN | https://url-shortener.me/5L85 | David | Indri Ariyani | In Progress | High | 2025-10-07 |  | Sudah Naik ke PROD, Saya tnya ke tim dlu ya mas, nnti di info lgi info dari pak david | bbc76c9d-b665-4623-8cdd-05d7d00cbe41
42 | BRD045 | Penambahan Kolom Kekayaan Bersih dan Penghapusan Kolom Asset di CIF Maintenance dan Tarikan Client List | https://url-shortener.me/5L4G | Yoga Dishtira | Yandhika Mardi Haposan | Completed | High | 2025-10-16 | 2025-12-24 | Done Bikin UAT dan CR | 757ca617-20f9-4391-b261-79cb8b5be1ed
43 | BRD046 | Perubahan email tujuan pelaporan pelanggaran di website Utrade |  | David Steven | Indri Ariyani | Completed | High | 2025-10-14 | 2025-10-23 |  | 0ffc8480-0fc1-44ff-82f7-01a026e56729
44 | BRD047 | Perubahan Nomor Rekening Bank untuk Transaksi RDN |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-10-22 | 2025-11-08 |  | 45e8c534-334d-482b-a233-42a9844e9eb7
45 | BRD048 | Change Mapping MKBD VD 6.6 and update saving balance reconciliation - bank KSEI |  | Yoga Dishtira | Meiliani Intania | Completed | High | 2025-10-22 | 2025-11-25 |  | b705f3db-fcb9-485f-8002-97efac5e8deb
46 | BRD049 | Redirect Website dari kh.co.id ke utrade.co.id | https://url-shortener.me/5L7N | David | Indri Ariyani | Completed | High | 2025-11-27 | 2026-01-12 | Done Bikin UAT dan CR | 21a65d4d-ad86-46a8-b884-1252df54126b
47 | BRD050 | Perubahan Logo UTRADE pada Website dan aplikasi UTRADE (Desktop, Website dan Mobile) |  | David,Gilang,Dimas, Deni | Indri Ariyani | Completed | High | 2025-11-17 | 2025-12-19 | Sudah di Email ke Tim S21 untuk di Update perbaikan kembali masih terdapat Logo UOB nya di SOA all Apps | 0d149aa4-1fd3-4a51-9b8f-4fc4ab5a3ba5
48 | BRD051 | Perubahan Nama PT Kay Hian Sekuritas pada Website |  | David Steven | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Done Bikin UAT dan CR | b46f5c65-cd90-4e1b-94e6-6cbb6aaa53f5
49 | BRD052 | Perubahan Nama PT pada UTRADE all Apps |  | Gilang, Dimas, Deni | Indri Ariyani | Completed | High | 2025-12-02 | 2025-12-12 | Sudah di naikan di PROD, Menunggu Konfirmasi dari Tim Ebiz | ebaa9b0c-0c13-486e-89ae-80866effb0f8
50 | BRD053 | Migrasi Web Report dan Web Research ke IP Local |  | David | Indri Ariyani | Completed | High | 2025-12-03 |  | Sudah di pindahkan migrasi ke Local webreport dan web research, menunggu Make sure dari tim Ebiz, info update ke david mengenai statusnya (sudah ok atau belum) | cc86d030-e614-42c4-b845-c3b3d4ac2584
51 | BRD054 | Perubahan nama PT dan Perubahan Logo PT di S21 Remote Trading | https://url-shortener.me/5L5U | Nabila | Rizky Saputra | In Progress | High | 2025-12-05 |  | Sudah di kirimkan perbaikanya dan menunggu dari tim IT untuk di naikin ke production dan merubah database company nya untuk pergantian namanya. | 2c438313-5a57-473c-aa3f-420faae9998a
52 | BRD055 | Perubahan nama PT dan Perubahan Logo PT di S21 Back Office |  | Yoga Dishtira | Rizky Saputra | Completed | High | 2025-12-17 | 2025-12-22 | Ubah logo manual ke user user yang blum ada logo di S21 BO Semua Divisi | e486a5da-f315-491f-b569-8a39bed37270
53 | BRD057 | Password Complexity S21 RT |  | Billy | Rizky Saputra | Completed | High | 2025-10-01 | 2025-10-03 |  | 9172454e-0366-4ea1-96fc-7d6d75199394
54 | BRD058 | 1. Unlock Mandatory data pada CIF Maintenance Institutional | https://url-shortener.me/5L8G | Yoga Dishtira | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | ok di development, mohon sekaligus permintaan BRD seperti permintaan email terlampir yang unloack all details | 18505d18-ed55-4f45-b783-12ead009efd2
55 | BRD059 | Change Notification Letter | https://url-shortener.me/5L4Q | Martin Haudy | Suci Yulianti Ayunita Putri | In Progress | High | 2025-12-17 |  | Habis di ALTER SP nya, Bagaimana Cara Check nya di S21 BO nya? | ca8def53-7191-4f65-86ca-31f34a29f20d
56 | BRD060 | Menu Watch List Automatic Risk Profile Nasabah Menjadi High Risk CIF Insitutional |  | Yoga Dishtira | Suci Yulianti Ayunita Putri | Completed | High | 2025-12-22 | 2025-12-24 | Done Bikin UAT dan CR | ab613a56-ea83-438b-a612-0eecd47b4889
57 | BRD061 | Unlock All Details data pada CIF Maintenance Institutional and Individu | https://url-shortener.me/5MP7 | Yoga Dishtira |  | In Progress | High | 2025-12-29 |  | Sudah diimplementasikan pada Environment Development, Menunggu tim CS Testing | a8b28e40-3f71-413e-b2fa-5607d4295d8b
58 | BRD062 | Json Mainfest. (emiten GOTO tidak tampil jika order pagi hari- Mobile versi 15) |  | Gilang Setiawan |  | In Progress | High | 2026-01-05 |  | Sedang di Test dengan Tim Ebiz di development | f85f9907-be79-4692-90f8-7a892649eb70
59 | BRD063 | Update Corporate Action Advice for Right & Warrant |  | Yoga Dishtira |  | In Progress | High | 2026-01-07 |  | Sedang di Test di Area Development oleh Elvaran | c5a8ca08-1bc1-48f6-891c-af4aa4914c66
60 | BRD064 | Minimum Fee IDR 50,000 ( Net Comm) For Transaction in Negotation Board |  | Yoga Dishtira |  | In Progress | High | 2026-01-07 |  | Sedang di testing oleh Tim Contracting sudah di area development | 098a31bd-31b4-49b6-816f-dc8c0168124f
61 | BRD065 | Supporting Information for tax report client MF |  | Yoga Dishtira |  | In Progress | High | 2026-01-08 |  | Sedang di testing oleh Tim Contracting sudah di area development | fdd2c3ef-b284-4bc1-a180-254604ddcebb
62 | BRD066 | Added another Field in Report Client List |  | Yoga Dishtira |  | In Progress | High | 2026-01-08 |  | Sudah di Area Prodction, Menunggu Konfirmasi dari tim CS | 72323f87-1e22-4683-b412-3109b44e3d6f